## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BHATPARA PIPE WATER SUPPLY SCHEME | SM/14975 | New | Material Requisition To Resource Division |  |  | RTOR000460/2023-2024 | 3984/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.21 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BHATPARA PIPE WATER SUPPLY SCHEME | SM/14975 | New | Material Requisition To Resource Division |  |  | RTOR000253/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 9.75 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BHATPARA PIPE WATER SUPPLY SCHEME | SM/14975 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Central Drilling | BHATPARA PIPE WATER SUPPLY SCHEME | SM/14975 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Bhatpara W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2023-2024 | 1820/CDD | 07/12/2023 | 31/08/2024 | UTTAM KUMAR CHATTERJEE | 23.35 | 22.5 | 96.35 | 100
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BHATPARA PIPE WATER SUPPLY SCHEME | SM/14975 | New | Material Requisition To Resource Division |  |  | RTOR000798/2023-2024 | 311/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 20.47 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BHATPARA PIPE WATER SUPPLY SCHEME | SM/14975 | New | Quotation for new service connection at Bhatpara PWSS PH-1. |  |  | BILL/00349/2024-2025 | BP-2024-25-171 | 01/07/2024 | 01/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.58 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BHATPARA PIPE WATER SUPPLY SCHEME | SM/14975 | New | Quotation for new service connection at Bhatpara PWSS PH-2. |  |  | BILL/00348/2024-2025 | BP-2024-25-170 | 01/07/2024 | 01/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.38 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BHATPARA PIPE WATER SUPPLY SCHEME | SM/14975 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHATPARA & MAHARUTBA Piped Water Supply Scheme under Mangolkote Block, District:-Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | J.E. katwa,Junior Engineer | ORD/000429/2023-2024 | 3328/BWD | 02/08/2023 | 01/10/2025 | KAMIRUL SK & CO. | 815.64 | 375.49 | 46.04 | 10
9 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | BHATPARA PIPE WATER SUPPLY SCHEME | SM/14975 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BHATPARA Water Supply Scheme [ Block- MANGALKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000831/2023-2024 | 4108/CMD | 29/08/2023 | 31/03/2025 | JAL PRAVAHIKA PVT LTD | 28.97 | 0 | 0 | 42
10 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | BHATPARA PIPE WATER SUPPLY SCHEME | SM/14975 | New | Material Requisition To Resource Division |  |  | RTOR000074/2024-2025 | 400/BWD | 17/01/2025 | 17/01/2025 | Resource Division | 3.7 | 0 | 0 | 0
Total | [13 empty] | 972.1 | 397.98 | 40.94