## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME | SM/14976 | New | Material Requisition To Resource Division |  |  | RTOR000203/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 11.5 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME | SM/14976 | New | Material Requisition To Resource Division |  |  | RTOR000507/2023-2024 | 4031/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 3.08 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME | SM/14976 | New | Material Requisition To Resource Division |  |  | RTOR000645/2023-2024 | 5094/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME | SM/14976 | New | BAHIRSARBAMANGALA-A Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000106/2023-2024 | 2297/BWD | 19/05/2023 | 18/05/2024 | MLG CONSTRUCTION | 371.05 | 0 | 0 | 30
5 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME | SM/14976 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME | SM/14976 | New | New Service connection for Bahir Sarbamangala (Part-A) PWSS TW-1. |  |  | BILL/02895/2023-2024 | BP-2023-24-624 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.85 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME | SM/14976 | New | New Service connection for Bahir Sarbamangala (Part-A) PWSS TW-2. |  |  | BILL/02896/2023-2024 | BP-2023-24-625 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.52 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME | SM/14976 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bahir Sarbamangala-A Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001050/2023-2024 | 4045/CMD | 29/08/2023 | 01/07/2025 | P.K. ENGINEERING | 29.35 | 0 | 0 | 45
Total | [13 empty] | 503.76 | 0 | 0