## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | New | Material Requisition To Resource Division |  |  | RTOR000205/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 5.77 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | New | Material Requisition To Resource Division |  |  | RTOR000534/2023-2024 | 4286/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 1.53 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | New | Material Requisition To Resource Division |  |  | RTOR000656/2023-2024 | 5101/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHAGABATIPUR, MACHKHARA & UDGARA Piped Water Supply Scheme under Raina ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000690/2023-2024 | 4386/BWD | 05/10/2023 | 04/10/2024 | SK ALIM | 1378.97 | 0 | 0 | 55
5 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-05-2024 to 31-07-2024) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000108/2024-2025 | 807/BSD | 29/04/2024 | 04/07/2024 | PARVIN BEGAM | 0.85 | 0 | 0 | 100
6 | PURBA BARDHAMAN | Raina-I | Central Mechanical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | New | New electric connection for Bhagabatipur PWSS, PH-1 |  |  | BILL/01886/2023-2024 | BP-2023-24-343 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.15 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-I | Central Mechanical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | New | New Service connection for BHAGABATIPUR W/S Scheme PH No.-1 |  |  | BILL/01795/2023-2024 | BP-2023-24-312 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.93 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina-I | Central Mechanical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
9 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | New | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 25/01/2026 | SK ALIM | 1353.91 | 0 | 0 | 25
10 | PURBA BARDHAMAN | Raina-I | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-08-2025 to 31-10-2025) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000703/2025-2026 | 2019/BSD | 31/07/2025 | 05/10/2025 | PARVIN BEGAM | 0.85 | 0 | 0 | 100
11 | PURBA BARDHAMAN | Raina-I | Central Mechanical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME | SM/14977 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bhagabatipur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000908/2023-2024 | 4172/CMD | 29/08/2023 | 15/04/2025 | SOUNAK ENTERPRISE | 29.71 | 0 | 0 | 90
Total | [13 empty] | 2877.7 | 0 | 0