## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-I | Burdwan Division | CHAKPUROHIT PIPED WATER SUPPLY SCHEME | SM/14978 | New | CHAK PUROHIT Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000197/2023-2024 | 2702/BWD | 08/06/2023 | 03/04/2024 | M/S PROCHESTA ENTERPRISE | 263.18 | 222.45 | 84.52 | 80
2 | PURBA BARDHAMAN | Raina-I | Central Mechanical | CHAKPUROHIT PIPED WATER SUPPLY SCHEME | SM/14978 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chak Purohit Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000576/2023-2024 | 3916/CMD | 21/08/2023 | 31/07/2024 | P.K. ENGINEERING | 28.9 | 22.79 | 78.86 | 96
3 | PURBA BARDHAMAN | Raina-I | Burdwan Division | CHAKPUROHIT PIPED WATER SUPPLY SCHEME | SM/14978 | New | Material Requisition To Resource Division |  |  | RTOR000269/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 9.34 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-I | Burdwan Division | CHAKPUROHIT PIPED WATER SUPPLY SCHEME | SM/14978 | New | Material Requisition To Resource Division |  |  | RTOR000485/2023-2024 | 4009/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.37 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-I | Burdwan Division | CHAKPUROHIT PIPED WATER SUPPLY SCHEME | SM/14978 | New | Material Requisition To Resource Division |  |  | RTOR000661/2023-2024 | 5102/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-I | Central Mechanical | CHAKPUROHIT PIPED WATER SUPPLY SCHEME | SM/14978 | New | New service connection charges for Chakpurohit PWSS TW-2 |  |  | BILL/01666/2023-2024 | BP-2023-24-221 | 10/11/2023 | 10/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.93 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-I | Central Mechanical | CHAKPUROHIT PIPED WATER SUPPLY SCHEME | SM/14978 | New | New service connection charges for Chakpurohit PWSS TW-1 |  |  | BILL/01527/2023-2024 | BP-2023-24-192 | 11/10/2023 | 11/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina-I | Central Mechanical | CHAKPUROHIT PIPED WATER SUPPLY SCHEME | SM/14978 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
9 | PURBA BARDHAMAN | Raina-I | Burdwan Division | CHAKPUROHIT PIPED WATER SUPPLY SCHEME | SM/14978 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-05-2024 to 31-07-2024) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000108/2024-2025 | 807/BSD | 29/04/2024 | 04/07/2024 | PARVIN BEGAM | 0.85 | 0.28 | 33.19 | 100
10 | PURBA BARDHAMAN | Raina-I | Burdwan Division | CHAKPUROHIT PIPED WATER SUPPLY SCHEME | SM/14978 | New | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 01/04/2027 | SK ALIM | 1353.91 | 0 | 0 | 55
Total | [13 empty] | 1762.41 | 245.52 | 13.93