## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME | SM/14979 | New | BAHIRSARBAMANGALA-B Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000107/2023-2024 | 2298/BWD | 19/05/2023 | 18/05/2024 | MLG CONSTRUCTION | 308.66 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME | SM/14979 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bahir Sarbamangala-B Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001049/2023-2024 | 4046/CMD | 29/08/2023 | 28/09/2023 | CHOUDHURY ENTERPRISE | 29.34 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME | SM/14979 | New | Material Requisition To Resource Division |  |  | RTOR000202/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 13.95 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME | SM/14979 | New | Material Requisition To Resource Division |  |  | RTOR000508/2023-2024 | 4032/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 6.34 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME | SM/14979 | New | Material Requisition To Resource Division |  |  | RTOR000646/2023-2024 | 5095/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
Total | [13 empty] | 378.75 | 0 | 0