## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME | SM/14980 | New | Material Requisition To Resource Division |  |  | RTOR000112/2022-2023 | 1646/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 1.65 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME | SM/14980 | New | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 1257/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 13.53 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME | SM/14980 | New | Material Requisition To Resource Division |  |  | RTOR000703/2023-2024 | 5061/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 19.78 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | JABAGRAM PIPED WATER SUPPLY SCHEME | SM/14980 | New | New Service connection charges for Jabagram W/S Scheme TW-I |  |  | BILL/00572/2023-2024 | BP-2023-24-8 | 12/05/2023 | 12/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.81 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME | SM/14980 | New | Continuation order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. (Sl No-1) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000930/2023-2024 | 1016/KTS | 20/09/2023 | 13/10/2023 | M/S MUNMUN DEY | 0.3 | 0.09 | 30.5 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | JABAGRAM PIPED WATER SUPPLY SCHEME | SM/14980 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | JABAGRAM PIPED WATER SUPPLY SCHEME | SM/14980 | New | NEW SERVICE CONNECTION FOR JABAGRAM PWSS TW-2. |  |  | BILL/00008/2024-2025 | BP-2024-25-1 | 04/04/2024 | 04/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.75 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME | SM/14980 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOHAGRAM, KHERUA & JABAGRAM Piped Water Supply Scheme under Mangalkote Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000697/2022-2023 | 582/BWD | 17/02/2023 | 01/01/2026 | PUSPA ENTERPRISE | 1185.88 | 380.48 | 32.08 | 75
9 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME | SM/14980 | New | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001301/2024-2025 | 936/BWD | 11/03/2025 | 07/09/2025 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | JABAGRAM PIPED WATER SUPPLY SCHEME | SM/14980 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JABAGRAM Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000035/2023-2024 | 2472/CMD | 30/05/2023 | 20/12/2024 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 28.96 | 23.24 | 80.24 | 88
Total | [13 empty] | 1679.39 | 403.81 | 24.04