## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | UNIATATARPUR PIPED WATER SUPPLY SCHEME | SM/15133 | New | Material Requisition To Resource Division |  |  | RTOR000332/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 10.34 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | UNIATATARPUR PIPED WATER SUPPLY SCHEME | SM/15133 | New | Material Requisition To Resource Division |  |  | RTOR000458/2023-2024 | 3982/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 2.76 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | UNIATATARPUR PIPED WATER SUPPLY SCHEME | SM/15133 | New | Material Requisition To Resource Division |  |  | RTOR000700/2023-2024 | 5070/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | UNIATATARPUR PIPED WATER SUPPLY SCHEME | SM/15133 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at UNIATATARPUR Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000824/2023-2024 | 4101/CMD | 29/08/2023 | 28/09/2023 | CHOUDHURY ENTERPRISE | 26.93 | 0 | 0 | 48
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | UNIATATARPUR PIPED WATER SUPPLY SCHEME | SM/15133 | New | Balance work for OHR, extension of pipeline to provide FHTC in Barulia & Narayanpur mouza with Sinking of Tube well, Construction of Pump house, Boundary Wall, Land Development, Plinth Protection for pump house & OHR under, approach road to 2nd pump house UNIATATARPUR PWSS, Katwa Sub Division, Block- Mongolkote, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000504/2024-2025 | 3162/BWD | 22/08/2024 | 20/12/2024 | POWER TOOLS & ENGINEERING | 152.52 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | UNIATATARPUR PIPED WATER SUPPLY SCHEME | SM/15133 | New | Quotation for new service connection for Unitatarpur PWSS PH-1 |  |  | BILL/00247/2024-2025 | BP-2024-25-127 | 31/05/2024 | 31/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.22 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | UNIATATARPUR PIPED WATER SUPPLY SCHEME | SM/15133 | New | Quotation for New service connection for Unitatarpur PWSS PH 2 |  |  | BILL/00248/2024-2025 | BP-2024-25-126 | 31/05/2024 | 31/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.78 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | UNIATATARPUR PIPED WATER SUPPLY SCHEME | SM/15133 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEULIA, GOBARDHANPUR, KHARIJA-KASHIGRAM & UNIATATARPUR Piped Water Supply Scheme under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000477/2023-2024 | 3491/BWD | 09/08/2023 | 01/11/2025 | POWER TOOLS & ENGINEERING | 1741.05 | 0 | 0 | 10
9 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | UNIATATARPUR PIPED WATER SUPPLY SCHEME | SM/15133 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 19/05/2025 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
Total | [13 empty] | 2019.71 | 0 | 0