## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME | SM/15151 | New | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 13.59 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME | SM/15151 | New | Material Requisition To Resource Division |  |  | RTOR000492/2023-2024 | 4016/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 0.97 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME | SM/15151 | New | Material Requisition To Resource Division |  |  | RTOR000631/2023-2024 | 4883/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 28.85 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | JAJIGRAM PIPE WATER SUPPLY SCHEME | SM/15151 | New | New service connection charges for Jajigram PWSS TW-2 |  |  | BILL/01539/2023-2024 | BP-2023-24-206 | 30/10/2023 | 30/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.31 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | JAJIGRAM PIPE WATER SUPPLY SCHEME | SM/15151 | New | New service connection charges for Jajigram PWSS TW-1 |  |  | BILL/01476/2023-2024 | BP-2023-24-174 | 29/09/2023 | 29/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.42 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME | SM/15151 | New | Balance work for Balance work of OHR, construction Concrete Road, 1st Floor of Office Building, Functional Household Tap Connection, land development, Road restoration etc. of Gopekhanji, Jajigram & Gidhagram PWSS under KATWA -I Block, under Katwa Sub Division under Burdwan Divn, District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000503/2024-2025 | 3161/BWD | 22/08/2024 | 20/12/2024 | POWER TOOLS & ENGINEERING | 272.54 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | JAJIGRAM PIPE WATER SUPPLY SCHEME | SM/15151 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | JAJIGRAM PIPE WATER SUPPLY SCHEME | SM/15151 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 09/02/2025 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME | SM/15151 | New | JAJIGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000742/2022-2023 | 1135/BWD | 13/03/2023 | 31/03/2025 | POWER TOOLS & ENGINEERING | 368.83 | 284.13 | 77.04 | 75
10 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME | SM/15151 | New | Construction of Office Cum Godown at Head work site of JAJIGRAM PWSS under Katwa Sub Division, within Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000854/2023-2024 | 5201/BWD | 29/11/2023 | 27/05/2024 | SUBODH KUMAR MONDAL | 37.69 | 32.7 | 86.77 | 10
11 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME | SM/15151 | New | Balance work for the construction of office cum Go-Down at ground floor at the head work site of JAJIGRAM PWSS under Katwa I Block under Katwa Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/001025/2024-2025 | 106/BWD | 07/01/2025 | 08/03/2025 | SUBODH KUMAR MONDAL | 9.11 | 0 | 0 | 0
Total | [13 empty] | 809.07 | 316.84 | 39.16