## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME | SM/15152 | Augmentation | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of AGRADWIP and its adjoining mouzas Piped Water Supply Scheme, Block Katwa II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000698/2022-2023 | 604/BWD | 17/02/2023 | 19/03/2023 | AUXILIARY TUBE WELL DRILLERS | 12.77 | 9.45 | 73.98 | 100
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME | SM/15152 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Agradip Kashipur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000079/2023-2024 | 2579/CMD | 07/06/2023 | 05/10/2024 | MITRA ENTERPRISE | 10.99 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME | SM/15152 | Augmentation | Installation of deptt.supplied Pump·motor set and other allied works at PH-1 of Aug. of Agradip Kashipur water supply scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000486/2024-2025 | 513/DIC/BMSD(D) | 20/08/2024 | 27/08/2024 | MITRA ENTERPRISE | 0.33 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME | SM/15152 | Augmentation | NEW SERVICE CONNECTION FOR AGRADIP KASHIPUR PWSS PH 1 |  |  | BILL/02954/2023-2024 | BP-2023-24-637 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.92 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME | SM/15152 | Augmentation | Augmentation of AGRADWIP Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman._2ND CALL | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000558/2023-2024 | 3778/BWD | 29/08/2023 | 01/01/2027 | MOTHER INFRASTRUCTURE | 420.6 | 327.93 | 77.97 | 86
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME | SM/15152 | Augmentation | Construction of Pump House, Boundary walls and Raising Main for Aug. of AGRADWIP Piped W/S. Scheme under Katwa-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000925/2023-2024 | 5485/BWD | 13/12/2023 | 07/01/2025 | JAMALUDDIN SK | 9.75 | 0 | 0 | 80
7 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME | SM/15152 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 2 at Augumentation of Agradip Kashipur (Babladanga) Water Supply Scheme [BLOCK- Katwa-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000544/2024-2025 | 2445/CMD | 07/08/2024 | 03/06/2025 | SUBRATA BHADRA | 11.63 | 0 | 0 | 91
Total | [13 empty] | 472.98 | 337.38 | 71.33