## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MAKHALTOR PIPED WATER SUPPLY SCHEME | SM/15153 | New | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 1260/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 6.59 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MAKHALTOR PIPED WATER SUPPLY SCHEME | SM/15153 | New | New service connection charges for Makhaltor W/S Scheme TW-2 |  |  | BILL/00697/2023-2024 | BP-2023-24-38 | 27/06/2023 | 27/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.11 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MAKHALTOR PIPED WATER SUPPLY SCHEME | SM/15153 | New | New service connection charges of Makhaltor W/S Scheme TW-1 |  |  | BILL/00687/2023-2024 | BP-2023-24-35 | 26/06/2023 | 26/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.3 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MAKHALTOR PIPED WATER SUPPLY SCHEME | SM/15153 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MAKHALTOR PIPED WATER SUPPLY SCHEME | SM/15153 | New | MAKHALTOR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000733/2022-2023 | 1050/BWD | 10/03/2023 | 01/01/2025 | HAMID SK | 195.79 | 198.13 | 101.2 | 99
6 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MAKHALTOR PIPED WATER SUPPLY SCHEME | SM/15153 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MAKHALTOR Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000108/2023-2024 | 2612/CMD | 08/06/2023 | 14/03/2024 | SOUNAK ENTERPRISE | 27.65 | 21.16 | 76.53 | 30
7 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MAKHALTOR PIPED WATER SUPPLY SCHEME | SM/15153 | New | Providing left out FHTC at different area under the command area of Makhaltore PWSS (SM/15153) in order to declare Sajal Gram and other anciallary works, Katwa II Block under Katwa Sub Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001310/2024-2025 | 1085/BWD | 28/03/2025 | 27/04/2025 | HAMID SK | 7.42 | 0 | 0 | 70
Total | [13 empty] | 300.03 | 219.29 | 73.09