## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Central Drilling | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Murgram W/S Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000173/2023-2024 | 1345/CDD | 13/09/2023 | 13/10/2023 | OSMAN SEKH | 16.61 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 1.38 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Material Requisition To Resource Division |  |  | RTOR000347/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 18.01 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Material Requisition To Resource Division |  |  | RTOR000744/2023-2024 | 5260/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.18 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MURGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000850/2023-2024 | 4122/CMD | 29/08/2023 | 28/09/2023 | S.K. ELECTRICALS | 27.77 | 19.55 | 70.38 | 46
6 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Supply & Delivery of 3 Phase actuator operated wafer type butterfly valve for Tube well No.- 1 at MURGRAM Water Supply Scheme [Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge |  | ORD/001622/2023-2024 | 348/DIC/BMSD(D) | 22/12/2023 | 29/12/2023 | SUBRATA BHADRA | 0.98 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Supply & delivery of Submersible Pumping Machinery, Suspension clamp and tube well cover etc. Tube well No.- 1 at MURGRAM Water Supply Scheme [ Block· KETUGRAM -1] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001627/2023-2024 | 25/DIC/BMSD(D) | 05/01/2024 | 12/01/2024 | SUBRATA BHADRA | 0.86 | 0.86 | 100 | 100
9 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Supply & delivery of valves, starter and Installation of Submersible Pumping Machinery for Tube well No. - 1 at MURGRAM Water Supply Scheme [ Block- KETUGRAM -1] under CMD, PHE Dte., Dist.· Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001633/2023-2024 | 48/DIC/BMSD(D) | 19/01/2024 | 03/02/2024 | SUBRATA BHADRA | 0.69 | 0.59 | 86.15 | 100
10 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Supply & Delivery of Submersible cable and column pipes for Tube Well No No:-1 at MURGRAM water supply scheme[ Block - KETUGRAM -1] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001629/2023-2024 | 41/DIC/BMSD(D) | 15/01/2024 | 22/01/2024 | SUBRATA BHADRA | 0.87 | 0.87 | 100 | 100
11 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Quotation for new service connection at Murgram W/S Scheme PH-II. |  |  | BILL/01807/2023-2024 | BP-2023-24-314 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.25 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Quotation for new service connection at Murgram W/S Scheme PH-I. |  |  | BILL/01808/2023-2024 | BP-2023-24-313 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.21 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | NEW SERVICE CONNECTION FOR MURGRAM PWSS PH-I. |  |  | BILL/00103/2024-2025 | BP-2024-25-44 | 26/04/2024 | 26/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.64 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000435/2023-2024 | 3387/BWD | 03/08/2023 | 01/01/2026 | PUSPA ENTERPRISE | 1333.98 | 221.92 | 16.64 | 40
15 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MURGRAM PIPED WATER SUPPLY SCHEME | SM/15156 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000289/2024-2025 | 2739/BWD | 12/07/2024 | 01/01/2025 | PUSPA ENTERPRISE | 185.75 | 24.12 | 12.98 | 72
Total | [13 empty] | 1698.46 | 267.9 | 15.77