## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME | SM/15159 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Gangatikuri Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000093/2023-2024 | 2584/CMD | 07/06/2023 | 06/06/2025 | M/S, S.S. ENTERPRISE. | 22.6 | 0 | 0 | 44
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME | SM/15159 | Augmentation | Augmentation of GANGATIKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000897/2023-2024 | 5375/BWD | 07/12/2023 | 01/01/2026 | S.S. ENTERPRISE | 194.38 | 93.32 | 48.01 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME | SM/15159 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme GANGATIKURI PWSS (Sl No-04) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000072/2023-2024 | 396/KTS | 13/04/2023 | 13/05/2023 | SIRCON ENGINEERING SERVICES | 2.49 | 2.49 | 100 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME | SM/15159 | Augmentation | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000683/2024-2025 | 1009/KTS | 19/07/2024 | 17/09/2024 | AJIT SAMANTA | 0.77 | 0.15 | 20 | 100
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME | SM/15159 | Augmentation | Yard lighting arrangement & allied works at Gangatikuri water supply scheme under Ketugram-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000408/2024-2025 | 2788/CMD | 01/10/2024 | 30/11/2024 | DILIP MAHATO | 15.98 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME | SM/15159 | Augmentation | Quotation for new service connection at Augmentation of Gangatikuri PWSS TW-1 |  |  | BILL/01093/2024-2025 | BP-2024-25-402 | 22/11/2024 | 22/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.88 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME | SM/15159 | Augmentation | Protection work for construction of concrete road along with other allied work in connection with Gangatikuri PWSs (SM/15159) under Ketugram II Block under Katwa Sub Division within Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001059/2024-2025 | 258/BWD | 14/01/2025 | 01/01/2026 | S.S. ENTERPRISE | 34.25 | 0 | 0 | 0
Total | [13 empty] | 275.35 | 95.97 | 34.85