## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 1.1 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | New | Material Requisition To Resource Division |  |  | RTOR000324/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 17.24 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | New | Material Requisition To Resource Division |  |  | RTOR000734/2023-2024 | 5233/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.37 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SITAHATI Water Supply Scheme [ Block- MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000875/2023-2024 | 4138/CMD | 29/08/2023 | 28/09/2023 | CHOUDHURY ENTERPRISE | 27.7 | 0 | 0 | 46
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | New | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | AE(HQs) | J.E. 1 BURDWAN | ORD/001212/2023-2024 | 907/BWD | 04/03/2024 | 03/04/2024 | MANASH GHOSH | 23.87 | 0 | 0 | 100
6 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 4118/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 18.62 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | New | NEW SERVICE CONNECTION FOR SITAHATI PWSS. |  |  | BILL/02863/2023-2024 | BP-2023-24-611 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.68 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | New | NEW SERVICE CONNECTION FOR SITAHATI PWSS. |  |  | BILL/02861/2023-2024 | BP-2023-24-612 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.43 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 19/05/2025 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
10 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PALISGRAM, PURBA NAYAPARA & SITAHATI Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000695/2023-2024 | 4364/BWD | 04/10/2023 | 01/04/2026 | M/S S. CHOUDHURY | 1505.07 | 0 | 0 | 77
11 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME | SM/15161 | New | Different types of works involve in connection with implementation of Aug. Mongalkote, Palishgram, Purba Nowapara, Sitahati, Singhi, Mejhiary & Karui Piped Water Supply Scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001191/2024-2025 | 873/BWD | 06/03/2025 | 02/09/2025 | M/S S. CHOUDHURY | 588.22 | 0 | 0 | 0
Total | [13 empty] | 2274.95 | 0 | 0