## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAKULIA, KULSANA & HALIMPUR Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | J.E. katwa,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000461/2023-2024 | 3443/BWD | 08/08/2023 | 21/11/2025 | ASHOK KUMAR GHOSH | 1588.1 | 86.62 | 5.45 | 15
2 | PURBA BARDHAMAN | Mangolkote | Central Drilling | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Chakulia W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000198/2023-2024 | 1339/CDD | 13/09/2023 | 10/04/2024 | M/S SAIKAT ENTERPRISE | 23.35 | 16.79 | 71.9 | 100
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 1.38 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Material Requisition To Resource Division |  |  | RTOR000288/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 7.8 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Material Requisition To Resource Division |  |  | RTOR000713/2023-2024 | 5047/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 19.78 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and Compound lighting arrangement for Tube well No.- 1 & 2 at CHAKULIA Water Supply Scheme [BLOCK- MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman | Driller In-Charge | Junior Engineer | ORD/001604/2023-2024 | 1534/CMD | 05/03/2024 | 21/11/2025 | CHATTERJEE ENTERPRISE | 28.81 | 6.9 | 23.94 | 70
8 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | AE(HQs) | J.E. 1 BURDWAN | ORD/001212/2023-2024 | 907/BWD | 04/03/2024 | 03/04/2024 | MANASH GHOSH | 23.87 | 5.35 | 22.42 | 100
9 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 4110/BWD | 25/11/2024 | 25/11/2024 | Resource Division | 9.28 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Quotation for new service connection for Chakulia PWSS TW-2. |  |  | BILL/00253/2024-2025 | BP-2024-25-133 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.1 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Quotation for new service connection for Chakulia PWSS TW-1. |  |  | BILL/00255/2024-2025 | BP-2024-25-134 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.57 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Additional quotation in second time against additional work at Chakulia PWSS TW-2 |  |  | BILL/00683/2024-2025 | BP-2024-25-268 | 21/08/2024 | 21/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.31 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME | SM/15162 | New | Balance work of CHAKULIA Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman | Assistant Engineer |  | ORD/001263/2024-2025 | 846/BWD | 05/03/2025 | 03/07/2025 | M/S M.M. ENTERPRISE | 214.08 | 0 | 0 | 0
Total | [13 empty] | 1987.5 | 115.66 | 5.82