## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Central Drilling | MORGRAM PIPED WATER SUPPLY SCHEME | SM/15163 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Morgram W/S Scheme (T/W-I & II) , Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000170/2023-2024 | 1346/CDD | 13/09/2023 | 13/10/2023 | S B S ENTERPRISE | 16.67 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME | SM/15163 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 3.97 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME | SM/15163 | New | Material Requisition To Resource Division |  |  | RTOR000745/2023-2024 | 5257/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.18 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME | SM/15163 | New | Material Requisition To Resource Division |  |  | RTOR000344/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 17.45 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MORGRAM PIPED WATER SUPPLY SCHEME | SM/15163 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MORGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000857/2023-2024 | 4125/CMD | 29/08/2023 | 28/09/2023 | JAGANNATH ENTERPRISE | 27.79 | 21.65 | 77.9 | 88
6 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MORGRAM PIPED WATER SUPPLY SCHEME | SM/15163 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MORGRAM PIPED WATER SUPPLY SCHEME | SM/15163 | New | Quotation for new service connection at Morgram W/S Scheme PH-II. |  |  | BILL/01806/2023-2024 | BP-2023-24-316 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | MORGRAM PIPED WATER SUPPLY SCHEME | SM/15163 | New | Quotation for new service connection at Morgram W/S Scheme PH-I. |  |  | BILL/01805/2023-2024 | BP-2023-24-315 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.76 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME | SM/15163 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000435/2023-2024 | 3387/BWD | 03/08/2023 | 01/01/2026 | PUSPA ENTERPRISE | 1333.98 | 142.34 | 10.67 | 40
10 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME | SM/15163 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000289/2024-2025 | 2739/BWD | 12/07/2024 | 01/01/2025 | PUSPA ENTERPRISE | 185.75 | 19.02 | 10.24 | 72
11 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME | SM/15163 | New | Extension work of pipe line MORGRAM Piped W/S. Scheme under Ketugram-I Block under Katwa Sub-Division within Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/001067/2023-2024 | 990/BWD | 06/03/2024 | 01/07/2025 | PUSPA ENTERPRISE | 133.47 | 128.97 | 96.63 | 82
Total | [13 empty] | 1829.01 | 311.98 | 17.06