## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 1.28 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | Material Requisition To Resource Division |  |  | RTOR000299/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 9.58 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | Material Requisition To Resource Division |  |  | RTOR000746/2023-2024 | 5254/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.18 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | CHAR SUJAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000179/2023-2024 | 3032/BWD | 14/07/2023 | 13/07/2024 | M/S H.R. CONSTRUCTION | 471.47 | 385.07 | 81.68 | 91
5 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 31/10/2024 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | New service connection for Char Sujapur PWSS PH-1. |  |  | BILL/02288/2023-2024 | BP-2023-24-414 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.99 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | New service connection for Char Sujapur PWSS PH-2. |  |  | BILL/02289/2023-2024 | BP-2023-24-415 | 19/01/2024 | 19/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.27 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house & OHR under Charsujapur PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000360/2024-2025 | 2923/BWD | 26/07/2024 | 24/10/2024 | M/S H.R. CONSTRUCTION | 81.31 | 0 | 0 | 2
9 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Char Sujapur Water Supply Scheme [ BLOCK- Ketugram-II] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001394/2024-2025 | 883/CMD | 26/03/2025 | 25/05/2025 | CHATTERJEE ENTERPRISE | 12.31 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAR SUJAPUR Water Supply Scheme [ Block- KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000866/2023-2024 | 4118/CMD | 29/08/2023 | 01/03/2025 | M/S. S.R. ENTERPRISE | 29.41 | 11.63 | 39.55 | 46
11 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | Material Requisition To Resource Division |  |  | RTOR000044/2024-2025 | 324/BWD | 15/01/2025 | 15/01/2025 | Resource Division | 6.23 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15165 | New | Qtn for new connection at Charsujapur T/W no-3 |  |  | BILL/00060/2025-2026 | 73 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.62 | 0 | 0 | 0
Total | [13 empty] | 686.6 | 396.71 | 57.78