## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for NABABHAT its Adjoining Mouza W/S Scheme, Block -Bardhaman-I within Burdwan Sub-Division, PHE Dte. (Mouza- KRISHNAPUR) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000830/2022-2023 | 499/BSD | 21/03/2023 | 05/05/2023 | BHASKAR NANDY | 3.16 | 0 | 0 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Balance work for Augmentation of Nababhat PWSS in connection with renovation and modification of administrative office complex building under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000450/2023-2024 | 3400/BWD | 03/08/2023 | 02/09/2023 | SANDIPAN SENGUPTA | 7.78 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Balance work for Augmentation of Nababhat PWSS in connection with renovation and modification of administrative office complex building under Burdwan Division PHE Dte. (Part - II). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | J.E. 1 BURDWAN | ORD/000849/2023-2024 | 5156/BWD | 24/11/2023 | 24/12/2023 | SANDIPAN SENGUPTA | 9.63 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | New service connection charges of Aug. Nababhat W/S Scheme TW-3 |  |  | BILL/00686/2023-2024 | BP-2023-24-31 | 23/06/2023 | 23/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.58 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of NABABHAT( Part-B)[BURDWAN-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000571/2023-2024 | 3899/CMD | 18/08/2023 | 17/09/2023 | CINZANO | 22.41 | 0 | 0 | 50
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Allied work for Augmentation of NABABHAT PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE,Junior Engineer, Burdwan Sadar Sub-Division | ORD/000432/2023-2024 | 3360/BWD | 02/08/2023 | 01/10/2023 | M/S ANAND CONSTRUCTION | 40.09 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Laying of inter connection between 3rd tube well site (Mouza-Krishnapur) and distribution system for Nababhat PWSS within Bardhaman-I Block , under Burdwan Division, PHE Dte |  |  | ORD/000942/2023-2024 | 2951/BSD | 19/12/2023 | 02/02/2024 | I.S. ENTERPRISE | 2.91 | 0 | 0 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Providing laying distrfrrrrribution pipe line at Amtala-Sukantapally due to construction of Road by gp for Nababhat PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000143/2024-2025 | 1031/BSD | 10/06/2024 | 10/07/2024 | SANDIPAN SENGUPTA | 0.96 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Providing laying distribution pipe line due to Constructioon of road by GP for NABABHAT PWSS under Burdwan-I Block of within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001190/2023-2024 | 536/BSD | 14/03/2024 | 13/04/2024 | NABAKUMAR DAS | 0.86 | 0 | 0 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tub well , Construction of pump house with Boundary wall & other related work for TALIT-SIMDAL (SM/18112), NABABHAT (SM-15166) and DEWANDIGHI-MIRJAPUR (SM/09494) PWSS under Burdwan Sub-Div., Block -Bwn-1, under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001248/2024-2025 | 793/BWD | 03/03/2025 | 01/07/2025 | M/S S.S. ENTERPRISE | 227.66 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Balance work for Augmentation of Nababhat PWSS in connection with upgradation of Approach Road, Land Development, etc for Head Works Site of Nababhat PWSS under Burdwan Division PHE Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/001208/2024-2025 | 661/BWD | 18/02/2025 | 20/03/2025 | M/S S. CHOUDHURY | 19.92 | 0 | 0 | 100
Total | [13 empty] | 337.95 | 0 | 0