## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for NABABHAT its Adjoining Mouza W/S Scheme, Block -Bardhaman-I within Burdwan Sub-Division, PHE Dte. (Mouza- KRISHNAPUR) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000830/2022-2023 | 499/BSD | 21/03/2023 | 05/05/2023 | BHASKAR NANDY | 3.16 | 2.73 | 86.42 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Balance work for Augmentation of Nababhat PWSS in connection with renovation and modification of administrative office complex building under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000450/2023-2024 | 3400/BWD | 03/08/2023 | 02/09/2023 | SANDIPAN SENGUPTA | 7.78 | 7.76 | 99.81 | 100
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | New service connection charges of Aug. Nababhat W/S Scheme TW-3 |  |  | BILL/00686/2023-2024 | BP-2023-24-31 | 23/06/2023 | 23/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.58 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of NABABHAT( Part-B)[BURDWAN-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000571/2023-2024 | 3899/CMD | 18/08/2023 | 17/09/2023 | CINZANO | 22.41 | 11.18 | 49.9 | 50
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Allied work for Augmentation of NABABHAT PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE,Junior Engineer, Burdwan Sadar Sub-Division | ORD/000432/2023-2024 | 3360/BWD | 02/08/2023 | 01/10/2023 | M/S ANAND CONSTRUCTION | 40.09 | 40.07 | 99.96 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Laying of inter connection between 3rd tube well site (Mouza-Krishnapur) and distribution system for Nababhat PWSS within Bardhaman-I Block , under Burdwan Division, PHE Dte |  |  | ORD/000942/2023-2024 | 2951/BSD | 19/12/2023 | 02/02/2024 | I.S. ENTERPRISE | 2.91 | 2.9 | 99.61 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Providing laying distrfrrrrribution pipe line at Amtala-Sukantapally due to construction of Road by gp for Nababhat PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000143/2024-2025 | 1031/BSD | 10/06/2024 | 10/07/2024 | SANDIPAN SENGUPTA | 0.96 | 0.92 | 95.2 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Providing laying distribution pipe line due to Constructioon of road by GP for NABABHAT PWSS under Burdwan-I Block of within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001190/2023-2024 | 536/BSD | 14/03/2024 | 13/04/2024 | NABAKUMAR DAS | 0.86 | 0.85 | 99.63 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tub well , Construction of pump house with Boundary wall & other related work for TALIT-SIMDAL (SM/18112), NABABHAT (SM-15166) and DEWANDIGHI-MIRJAPUR (SM/09494) PWSS under Burdwan Sub-Div., Block -Bwn-1, under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001248/2024-2025 | 793/BWD | 03/03/2025 | 01/07/2025 | M/S S.S. ENTERPRISE | 227.66 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Balance work for Augmentation of Nababhat PWSS in connection with upgradation of Approach Road, Land Development, etc for Head Works Site of Nababhat PWSS under Burdwan Division PHE Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/001208/2024-2025 | 661/BWD | 18/02/2025 | 20/03/2025 | M/S S. CHOUDHURY | 19.92 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Supply & Installation of submersible pumping machinery, different electro-mechanical works for Nababhat w/s scheme, T.W. No.-I (Replacement tubewell) and Power Backup arrangement at the office of the Burdwan Division & Durgapur w/s Division including RWS, Purba Bardhaman under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000324/2024-2025 | 2695/CMD | 11/09/2024 | 01/06/2025 | CHOUDHURY ENTERPRISE | 24.83 | 0 | 0 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Restoration of Road damaged by laying of Pipeline with ballah piling work at different location for NABABHAT Piped Water Supply Scheme, Block- Burdwan -I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000282/2024-2025 | 2714/BWD | 11/07/2024 | 01/01/2025 | GENUINE ENGINEERS CO-OP. SOCIETY LTD. | 17.93 | 3.62 | 20.16 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Sinking of 250 X 200 mm dia Tube Well (Replace) 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Head works TW site of NABABHAT Scheme under Burdwan - I Block within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001076/2024-2025 | 372/BWD | 16/01/2025 | 15/02/2025 | DAS CONSTRUCTION | 12.27 | 0 | 0 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Providing laying parallal distribution pipe line from Krishnapur pump to Kishnapur Baganpara for Nababhat PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001078/2024-2025 | 373/BWD | 16/01/2025 | 31/05/2025 | M/S ANAND CONSTRUCTION | 5.97 | 0 | 0 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Laying of inter connection between Replace tube well H/W site and distribution system for NABABHAT PWSS within Bardhaman-I Block, under Burdwan Division, PHE Dte. |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000174/2025-2026 | 1548/BSD | 02/07/2025 | 15/09/2025 | M/S PURBASHA | 0.51 | 0 | 0 | 100
Total | [13 empty] | 389.82 | 70.03 | 17.96