## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Central Drilling | KULUTIA PIPED WATER SUPPLY SCHEME | SM/15167 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Kulutia W/S Scheme (T/W-I & II) ,Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000165/2023-2024 | 1349/CDD | 13/09/2023 | 13/10/2023 | UNIVERSAL ENTERPRISES | 16.66 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | KULUTIA PIPED WATER SUPPLY SCHEME | SM/15167 | New | Material Requisition To Resource Division |  |  | RTOR000390/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 10.23 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | KULUTIA PIPED WATER SUPPLY SCHEME | SM/15167 | New | Material Requisition To Resource Division |  |  | RTOR000407/2023-2024 | 3825/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 2.16 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | KULUTIA PIPED WATER SUPPLY SCHEME | SM/15167 | New | Material Requisition To Resource Division |  |  | RTOR000740/2023-2024 | 5240/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.18 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | KULUTIA PIPED WATER SUPPLY SCHEME | SM/15167 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | KULUTIA PIPED WATER SUPPLY SCHEME | SM/15167 | New | New Service connection at Kulutia PWSS TW NO. 1 |  |  | BILL/02370/2023-2024 | BP-2023-24-491 | 01/02/2024 | 01/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.01 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | KULUTIA PIPED WATER SUPPLY SCHEME | SM/15167 | New | New service connection for Kulitia PWSS PH-2. |  |  | BILL/02910/2023-2024 | BP-2023-24-623 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | KULUTIA PIPED WATER SUPPLY SCHEME | SM/15167 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMEGERIA, ARGUN, CHINISPUR & KULUTIA Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000533/2023-2024 | 3630/BWD | 21/08/2023 | 01/09/2026 | M/S GOUTAM DAS | 1421.7 | 139.29 | 9.8 | 75
9 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | KULUTIA PIPED WATER SUPPLY SCHEME | SM/15167 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KULUTIA Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000856/2023-2024 | 4124/CMD | 29/08/2023 | 30/04/2025 | KAMAKHYA ENTERPRISE | 26.93 | 0 | 0 | 46
Total | [13 empty] | 1587.35 | 139.29 | 8.77