## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Central Drilling | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Chatka W/S Scheme (T/W-I & II), Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000174/2023-2024 | 1344/CDD | 13/09/2023 | 13/10/2023 | OSMAN SEKH | 16.61 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | CHATKA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000352/2023-2024 | 3065/BWD | 17/07/2023 | 01/01/2025 | M/S H.R. CONSTRUCTION | 402.79 | 365.97 | 90.86 | 86
3 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHATKA Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000867/2023-2024 | 4117/CMD | 29/08/2023 | 07/09/2025 | SOUNAK ENTERPRISE | 28.48 | 22.2 | 77.94 | 90
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | Material Requisition To Resource Division |  |  | RTOR000304/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 2.18 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | Material Requisition To Resource Division |  |  | RTOR000430/2023-2024 | 3856/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 0.69 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | Material Requisition To Resource Division |  |  | RTOR000738/2023-2024 | 5232/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.18 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | New service connection charges for Chatka PWSS TW-2 |  |  | BILL/01768/2023-2024 | BP-2023-24-277 | 21/12/2023 | 21/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.06 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | New service connection charges for Chatka PWSS TW-1 |  |  | BILL/01767/2023-2024 | BP-2023-24-276 | 21/12/2023 | 21/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.85 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Chakta, Mahula, Rajoor and Srigram PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000284/2024-2025 | 2721/BWD | 11/07/2024 | 01/10/2025 | ESCON INDIA | 139.35 | 21.22 | 15.23 | 70
11 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 309/BWD | 15/01/2025 | 15/01/2025 | Resource Division | 12.09 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME | SM/15168 | New | Operation & Maintenance of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of CHAKTA PWSS within Katwa Sub-Division under Burdwan Division, PHE Dte. [Period for 01.02.2026 to 31.03.2026 i.e 02(Two) Months]. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001284/2025-2026 | 82-1/KTS | 30/01/2026 | 30/03/2026 | ABHA ENTERPRISE | 0.79 | 0 | 0 | 0
Total | [13 empty] | 714.36 | 409.39 | 57.31