## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 37.55 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | New service connection charges for Gopkhanji PWSS TW-2 |  |  | BILL/00822/2023-2024 | BP-2023-24-100 | 03/08/2023 | 03/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.87 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | New service connection charges for Gopkhanji W/S Scheme TW-1 |  |  | BILL/00696/2023-2024 | BP-2023-24-39 | 27/06/2023 | 27/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.65 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-I | Burdwan Division | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | GOPKHANJI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000741/2022-2023 | 1134/BWD | 13/03/2023 | 31/07/2025 | POWER TOOLS & ENGINEERING | 482.85 | 0 | 0 | 74
5 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GOPKHANJI Water Supply Scheme [ Block- KATWA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000127/2023-2024 | 2660/CMD | 16/06/2023 | 16/07/2023 | JYOTY SOLAR POWER. | 26.98 | 0 | 0 | 100
7 | PURBA BARDHAMAN | Katwa-I | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 09/02/2025 | S DUTTA | 15.06 | 0 | 0 | 0
Total | [13 empty] | 625.12 | 0 | 0