## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GHUNI & JOYKRISHNAPUR Piped Water Supply Scheme under Purbasthali II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000492/2023-2024 | 3510/BWD | 10/08/2023 | 26/10/2025 | BKB INFRA PROJECTS PRIVATE LIMITED | 551.42 | 140.37 | 25.46 | 20
2 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JOYKRISHNAPUR Water Supply Scheme [ Block- PURBASTHALI-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000880/2023-2024 | 4143/CMD | 29/08/2023 | 05/06/2025 | JYOTY SOLAR POWER. | 26.98 | 0 | 0 | 45
3 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at Joykrishnapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000763/2022-2023 | 839/CMD | 20/02/2023 | 22/03/2023 | MS MANABESH ROY | 10.14 | 9.61 | 94.74 | 100
4 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 at Joykrishnapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000762/2022-2023 | 838/CMD | 20/02/2023 | 22/03/2023 | C.M. ENTERPRISE | 10.43 | 9.62 | 92.24 | 100
5 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Material Requisition To Resource Division |  |  | RTOR000540/2023-2024 | 4288/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 0.55 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Material Requisition To Resource Division |  |  | RTOR000297/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 12.33 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Material Requisition To Resource Division |  |  | RTOR000513/2023-2024 | 4037/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 37.2 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Laying of Rising main in between Tube Well and Distribution Line for Shimulia Village in Galsi -II Block under Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000396/2024-2025 | 621/DSD | 05/08/2024 | 04/09/2024 | MAA MAHAMAYA CONSTRUCTION | 2.15 | 2.13 | 98.71 | 100
9 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR JOYKRISHNAPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE.". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000569/2024-2025 | 1015/KSD | 07/08/2024 | 22/08/2024 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 99.69 | 100
10 | PURBA BARDHAMAN | Purbasthali-II | Durgapur W/S Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Acceptance cum Formal Work order for Laying of interconnection for PH NO-3 (At Taranagar) Pipe Line for under JOYKRISHNAPUR PWSS, Galsi-II Block, under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_3 | ORD/000162/2024-2025 | 1410/DWSD | 01/10/2024 | 30/11/2024 | MUNSHI JAVEDUR JAMAN | 0.63 | 0.58 | 91.86 | 100
11 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | New service connection charges for Joykrishnapur PWSS TW-1 |  |  | BILL/02191/2023-2024 | BP-2023-24-390 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.39 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | NEW SERVICE CONNECTION FOR JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME. |  |  | BILL/02828/2023-2024 | BP-2023-24-592 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Quotation for new service connection at Joykrishnapur PWSS PH-2 |  |  | BILL/01817/2023-2024 | BP-2023-24-333 | 03/01/2024 | 03/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.33 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Purbasthali-II | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Quotation for new service connection at Joykrishnapur W/S Scheme for PH No-1 |  |  | BILL/01820/2023-2024 | BP-2023-24-332 | 03/01/2024 | 03/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.57 | 0 | 0 | 0
15 | PURBA BARDHAMAN | Purbasthali-II | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Construction of 350cum OHR & Other Allied Works in connection with Augmentation of (SM/07803), (SM/09410), (SM/16304), (SM/15172) & (SM/14020) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001048/2024-2025 | 220/BWD | 10/01/2025 | 07/10/2025 | R.K. MANDAL& CO. | 491.79 | 0 | 0 | 1
16 | PURBA BARDHAMAN | Purbasthali-II | Durgapur W/S Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/15172 | New | Material Requisition To Resource Division |  |  | RTOR000058/2024-2025 | 478/DWSD | 17/03/2025 | 17/03/2025 | Resource Division | 0.14 | 0 | 0 | 0
Total | [13 empty] | 1172.15 | 162.97 | 13.9