## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK | SM/15173 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SEHERA( Part-B)[RAINA-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001076/2023-2024 | 4200/CMD | 29/08/2023 | 28/09/2023 | AMUSAR IMPEX PVT. LTD. | 24.39 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK | SM/15173 | Augmentation | Functional Household Tap Connection (FHTC) for Sehera, Mogolmari, Kona Krishnapur village for Augmentation of SEHERA Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001086/2023-2024 | 1112/BWD | 13/03/2024 | 12/05/2024 | PAL CONSTRUCTION | 35.49 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK | SM/15173 | Augmentation | Making illumination arrangement and mise works at Aug. of Sheherabazar water supply scheme RAINA-I BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000481/2024-2025 | 2952/CMD | 20/11/2024 | 11/07/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 17.51 | 0 | 0 | 30
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK | SM/15173 | Augmentation | Providing leftout FHTC, Const. of Boundary Wall (HW Site & 2nd TW Site), Drain, Pathway and land development at Head Work site & 2nd TW Site (Replacement), Rising main connection of 2nd TW (Replacement) with necessary repairing work for SEHERA Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001017/2024-2025 | 63/BWD | 06/01/2025 | 06/04/2025 | H SAMANTA | 41.78 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK | SM/15173 | Augmentation | Laying of Interconnection of Head work site New Tube well of Sehera Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001276/2023-2024 | 738/BSD | 20/04/2023 | 05/05/2023 | M/S UNIT CONSTRUCTION | 0.95 | 0 | 0 | 100
Total | [13 empty] | 120.12 | 0 | 0