## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Preparation and Submission of DPR for Augmentation of Hatgobindapur PWSS under Burdwan-II Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000350/2023-2024 | 1477/BSD | 12/07/2023 | 27/07/2023 | MEASURE LAND | 0.78 | 0.77 | 99.01 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation under HATGOBINDAPUR Piped W/S. Scheme within Burdwan - II Block under Burdwan Division, P.H.E Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000014/2023-2024 | 1729/BWD | 13/04/2023 | 01/10/2024 | GUPTA ENTERPRISE | 89.36 | 70.5 | 78.89 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Laying of interconnection between 1st & 2nd tube well to OHR for Hatgobindapur PWSS within Burdhaman-II Block under Burdwan Division, PHE Dte. |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001065/2024-2025 | 103/BSD | 16/01/2025 | 03/03/2025 | I.S. ENTERPRISE | 3.6 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Different works related (Sinking of Tube well-4th, Rising Main, construction of Pump House cum switch room and Boundary wall for HATGOBINDAPUR Piped Water Supply Scheme under BURDWAN -II Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000280/2024-2025 | 2712/BWD | 11/07/2024 | 01/04/2025 | DEY NIRMAN | 41.51 | 27.33 | 65.84 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Providing LDS in place of AC pipe line for HATGOBINDAPUR PWSS under Bardhaman-II Block within Burdwan Div. PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001278/2024-2025 | 874/BWD | 06/03/2025 | 30/08/2025 | DEY NIRMAN | 35.37 | 0 | 0 | 100
Total | [13 empty] | 170.63 | 98.59 | 57.78