## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Preparation and Submission of DPR for Augmentation of Hatgobindapur PWSS under Burdwan-II Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000350/2023-2024 | 1477/BSD | 12/07/2023 | 27/07/2023 | MEASURE LAND | 0.78 | 0 | 0 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Crossing of Bardhaman-Kalna Road near Hatgobindapur College More with 150 mm dia. pipeline through pushing of 600 mm. dia. RCC casing pipe by hydraulic jacking method for Hatgobindapur W/S. Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001199/2024-2025 | 644/BWD | 17/02/2025 | 27/02/2025 | I.S. ENTERPRISE | 5.57 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation under HATGOBINDAPUR Piped W/S. Scheme within Burdwan - II Block under Burdwan Division, P.H.E Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000014/2023-2024 | 1729/BWD | 13/04/2023 | 01/10/2024 | GUPTA ENTERPRISE | 89.36 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Laying of interconnection between 1st & 2nd tube well to OHR for Hatgobindapur PWSS within Burdhaman-II Block under Burdwan Division, PHE Dte. |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001065/2024-2025 | 103/BSD | 16/01/2025 | 03/03/2025 | I.S. ENTERPRISE | 3.6 | 0 | 0 | 100
Total | [13 empty] | 99.31 | 0 | 0