## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Preparation and Submission of DPR for Augmentation of Hatgobindapur PWSS under Burdwan-II Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000350/2023-2024 | 1477/BSD | 12/07/2023 | 27/07/2023 | MEASURE LAND | 0.78 | 0.77 | 99.01 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Crossing of Bardhaman-Kalna Road near Hatgobindapur College More with 150 mm dia. pipeline through pushing of 600 mm. dia. RCC casing pipe by hydraulic jacking method for Hatgobindapur W/S. Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001199/2024-2025 | 644/BWD | 17/02/2025 | 27/02/2025 | I.S. ENTERPRISE | 5.57 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Banagram village of Burdwan-II Block under Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000488/2025-2026 | 2347/BSD | 21/08/2025 | 31/08/2025 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.72 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Ramnagar village of Burdwan-II Block under Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte(5 nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000501/2025-2026 | 2348/BSD | 21/08/2025 | 31/08/2025 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.72 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR | SM/15175 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Hatkanda village of Burdwan-II Block under Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. (5 nos. Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000489/2025-2026 | 2360/BSD | 21/08/2025 | 31/08/2025 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.72 | 0 | 0 | 100
Total | [13 empty] | 8.52 | 0.77 | 9.03