## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) | SM/15178 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of SATGACHIA(Z-I, Part-B)[MEMARI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman |  |  | ORD/000934/2023-2024 | 4197/CMD | 29/08/2023 | 28/09/2023 | DAS TRADING CO. | 24.41 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) | SM/15178 | Augmentation | Illumination arrangement & different electro-mechanical works at SATGACHIA (Zone-I, Part-B) water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000417/2024-2025 | 2801/CMD | 01/10/2024 | 30/11/2024 | S.K. ELECTRICALS | 12.53 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) | SM/15178 | Augmentation | Restoration of Pump House at Head Work site of Satgachia Zone-I Piped water supply scheme at Memari-II BlockUnder Burdwan Division, Dist.-Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000179/2024-2025 | 998/BSD | 06/06/2024 | 06/07/2024 | INDRAJIT MONDAL | 0.96 | 0 | 0 | 90
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) | SM/15178 | Augmentation | NEW SERVICE CONNECTION FOR AUGMENTATION OF SATGACHIA PWSS |  |  | BILL/02825/2023-2024 | BP-2023-24-593 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.58 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) | SM/15178 | Augmentation | 150MM DI bypass pipeline at DVC Canel side for smooth water supply for FHTC from Patra mouza to Katna, Shrirampur & Begunia mouza under satgachia zone- I pwss within Memari- II block under Burdwan Division PHE DTE. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001335/2024-2025 | 633/BSD | 19/03/2025 | 18/04/2025 | M/S ANAND CONSTRUCTION | 4.94 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) | SM/15178 | Augmentation | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 03/07/2025 | PROJECT INDIA | 394.29 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) | SM/15178 | Augmentation | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001192/2024-2025 | 611/BWD | 11/02/2025 | 10/08/2025 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 0 | 25
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) | SM/15178 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-I W/S Scheme at DEBIPUR Mouza under Memari-I Block and SATGACHIA Z-I W/S Scheme at BEGUNIA Mouza under Memari-II Block within Burdwan Sub-Division, PHE Dte. [For 02 Nos. Tube well]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000192/2023-2024 | 2687/BWD | 08/06/2023 | 07/08/2023 | ANIRUDDHA FARUQUE | 26.48 | 0 | 0 | 50
Total | [13 empty] | 823.32 | 0 | 0