## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH | SM/15179 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Ghosh Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000100/2023-2024 | 2588/CMD | 07/06/2023 | 07/07/2023 | SUDIPTA GHOSH | 11.26 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH | SM/15179 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of GHOSH W/S Scheme under Memari-I Block within Burdwan Sub-Division, PHE Dte. [For Bahabpur village]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000200/2023-2024 | 2703/BWD | 08/06/2023 | 08/07/2023 | DAS CONSTRUCTION | 13.25 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH | SM/15179 | Augmentation | Construction of switch rooms & Rising main at different TW site for GHOSH Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000865/2023-2024 | 5296/BWD | 01/12/2023 | 30/01/2024 | TRIYA CONSTRUCTION | 8.94 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH | SM/15179 | Augmentation | Preparation and Submission of DPR for Augmentation of GHOSH PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] |  |  | ORD/000365/2023-2024 | 1527/BSD | 17/07/2023 | 01/08/2023 | MEASURE LAND | 0.78 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH | SM/15179 | Augmentation | Supply & Installation of voltage correcting device. LED fixture set & allied works at GHOSH Water Supply Scheme PH-II under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000148/2024-2025 | 1037/CMSD | 26/07/2024 | 25/08/2024 | BENGAL ELECTRICAL CONSTRUCTION | 3.28 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH | SM/15179 | Augmentation | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for GHOSH PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001193/2024-2025 | 612/BWD | 11/02/2025 | 12/05/2025 | PAL CONSTRUCTION | 29.22 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH | SM/15179 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Mandaljana village of Memari-I Block under Ghosh Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. (5 nos Board) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000496/2025-2026 | 2365/BSD | 21/08/2025 | 31/08/2025 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH | SM/15179 | Augmentation | Allied work of Laying distribution system for FHTC work for GHOSH Piped Water Supply Scheme at Bahabpur mouza within MEMARI - I BLOCK under Burdwan Division, PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001083/2024-2025 | 113/BSD | 16/01/2025 | 02/03/2025 | A.R. TRADERS | 4.7 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH | SM/15179 | Augmentation | Extension of pipeline & Left out FHTC Connection work for GHOSH Piped Water Supply Scheme at Bahabpur village [200 Nos], Andur [40 Nos], Tanti Gantar [80 Nos], Kabirpur [48 Nos], Total 368 Nos FHTC Work for Sajal Gram within Memari-I Block including leftout household water tap connection (FHTC) under BURDWAN Division, P.H.E Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/001075/2023-2024 | 1021/BWD | 07/03/2024 | 06/02/2025 | SKILLS AND FACILITY TRAINING INSTITUTE | 21.53 | 0 | 0 | 99
Total | [13 empty] | 93.69 | 0 | 0