## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) | SM/15182 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SATGACHIA(Z-II, Part-B)[MEMARI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001075/2023-2024 | 4199/CMD | 29/08/2023 | 28/09/2023 | DAS TRADING CO. | 24.41 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) | SM/15182 | Augmentation | Sinking of Tube-well, construction of switch rooms & Rising main at 3RD TW site for SATGACHIA ZONE-II Piped Water Supply Scheme under MEMARI-II Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000899/2023-2024 | 5357/BWD | 06/12/2023 | 04/02/2024 | J K CORPORATION | 20.1 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) | SM/15182 | Augmentation | Construction of boundary wall and Land development with approach road including internal drain at 2ND TW site for SATGACHIA ZONE-II PWSS under Memari-II Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000948/2023-2024 | 5595/BWD | 20/12/2023 | 19/01/2024 | GOUTAM KUMAR MITRA | 5.09 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) | SM/15182 | Augmentation | Restoration of Pump House at Head Work site of SATGACHIA ZONE-II Piped water supply scheme at Memari-II Block under Burdwan Division, Dist.-Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000137/2024-2025 | 1002/BSD | 06/06/2024 | 06/07/2024 | SAANVI ENTERPRISE | 0.96 | 0 | 0 | 10
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) | SM/15182 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone- I & II, Tube well No.- I (Replacement tube well) at Satgachia Water Supply Scheme [ BLOCK- Memari-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000531/2024-2025 | 3071/CMD | 03/12/2024 | 01/02/2025 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 25.34 | 0 | 0 | 95
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) | SM/15182 | Augmentation | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 03/07/2025 | PROJECT INDIA | 394.29 | 0 | 0 | 0
Total | [13 empty] | 470.2 | 0 | 0