## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for SHYAMSUNDAR its Adjoining Mouza W/S Scheme, Block -Raina-I within Burdwan Sub-Division, PHE Dte. (Mouza- Gopinathpur) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000770/2022-2023 | 505/BSD | 21/03/2023 | 05/05/2023 | JYOTI ENTERPRISE | 3.5 | 2.76 | 78.84 | 100
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | New service connection charges for Aug. Shyamsundar PWSS TW-4 |  |  | BILL/01425/2023-2024 | BP-2023-24-150 | 05/09/2023 | 05/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.25 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | New service connection charges for Aug. of Shyamsundar PWSS TW-1 |  |  | BILL/00855/2023-2024 | BP-2023-24-104 | 07/08/2023 | 07/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.18 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Construction of Pathway at Head Work site for SHYAMSUNDAR PIPED WATER SUPPLY SCHEME , Block- Raina-I , within Burdwan Sub Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000154/2024-2025 | 1040/BSD | 10/06/2024 | 10/07/2024 | POMPA CONSTRUCTION CO. | 0.93 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Laying Parallel Pipeline, providing FHTC and Repairing of Pump House at 2nd Tube Well Site for Aug. of SHYAMSUNDAR Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000224/2024-2025 | 2524/BWD | 03/07/2024 | 01/10/2024 | DEBASHISH ENTERPRISE | 22.66 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Augmentation of SHYAMSUNDAR Piped Water Supply Scheme with LDS, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test, Construction of boundary wall at Head works & 2nd TW site & FHTC under Raina ¿ I Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000598/2021-2022 | 1474/BWD | 14/03/2022 | 14/03/2023 | SK ALIM | 474.78 | 61.66 | 12.99 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Allied works for Augmentation of SHYAMSUNDAR W/S Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000346/2023-2024 | 3035/BWD | 14/07/2023 | 12/10/2023 | SK ALIM | 113.11 | 94.14 | 83.23 | 100
8 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Making illumination arrangement and mise works at SHYAMSUNDAR water supply scheme RAINA-I BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000474/2024-2025 | 2954/CMD | 20/11/2024 | 19/01/2025 | CHATTERJEE ENTERPRISE | 14.87 | 0 | 0 | 30
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Muktipur village of Raina-I Block under Shyamsundar Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000617/2025-2026 | 2369/BSD | 21/08/2025 | 31/08/2025 | S.M. ENGOCON | 0.72 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SHYAMSUNDAR(Part-B)[RAINA-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000569/2023-2024 | 3901/CMD | 18/08/2023 | 30/05/2024 | SOUNAK ENTERPRISE | 24.41 | 23.77 | 97.37 | 90
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Construction of Drain at Head Work site for SHYAMSUNDAR PIPED WATER SUPPLY SCHEME , Block- Raina-I , within Burdwan Sub Division under Burdwan Division PHE Dte |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000148/2024-2025 | 1041/BSD | 10/06/2024 | 10/07/2024 | LAKSHMIKANTA DAS | 0.93 | 0 | 0 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Restore of pipeline damaged by construction of Pathashree Road near Muktipur Village for SHYAMSUNDAR PIPED WATER SUPPLY SCHEME , Block- Raina-I , within Burdwan Sub Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000518/2024-2025 | 1865/BSD | 22/08/2024 | 21/09/2024 | MAA MAHAMAYA CONSTRUCTION | 0.97 | 0 | 0 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Restore of pipeline damaged by construction of pathashree road near Surya Pally for SHYAMSUNDAR Piped Water Supply Scheme,Block:Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001020/2024-2025 | 10/BSD | 02/01/2025 | 17/01/2025 | MAA MAHAMAYA CONSTRUCTION | 0.97 | 0 | 0 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Re- Connection of existing FHTC [54Nos.] damaged by construction of PATHASHREE ROAD for SHYAMSUNDA RPIPED WATER SUPPLY SCHEME,Block-Raina-I,within Burdwan Sub Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000515/2024-2025 | 1862/BSD | 22/08/2024 | 21/09/2024 | MAA MAHAMAYA CONSTRUCTION | 0.95 | 0.25 | 26.08 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Restore of pipeline damaged by construction of pathashree road near Shyamsundar Grils School for SHYAMSUNDAR Piped Water Supply Scheme,Block:Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001284/2024-2025 | 506/BSD | 06/03/2025 | 05/04/2025 | MAA MAHAMAYA CONSTRUCTION | 0.95 | 0 | 0 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS | SM/15183 | Augmentation | Laying Parallel Pipeline along Pathashree Road from Girls School to Muktipur Village for SHYAMSUNDAR PIPED WATER SUPPLY SCHEME, Block- Raina-I , within Burdwan Sub Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001198/2024-2025 | 102/BSD | 16/01/2025 | 15/02/2025 | MAA MAHAMAYA CONSTRUCTION | 4.08 | 0 | 0 | 100
Total | [13 empty] | 675.25 | 182.58 | 27.04