## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | Augmentation | Preparation and Submission of DPR for Augmentation of ABUJHATI PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000364/2023-2024 | 1526/BSD | 17/07/2023 | 01/08/2023 | MEASURE LAND | 0.78 | 0 | 0 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | Augmentation | Laying of HDPE Pipeline from 4th Number Pump House to main distribution system for ABUJHATI Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. |  |  | ORD/000722/2023-2024 | 3925/BWD | 05/09/2023 | 05/10/2023 | MAA BHABANI CONSTRUCTION | 21.04 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | Augmentation | New service connection charges for Abujhati PWSS TW-4 |  |  | BILL/00765/2023-2024 | BP-2023-24-66 | 20/07/2023 | 20/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augmentation of ABUJHATI[JAMALPUR] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000568/2023-2024 | 3902/CMD | 18/08/2023 | 17/09/2023 | KUNDU CONSTRUCTION. | 12.25 | 0 | 0 | 95
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | Augmentation | Extension of CIDF/D.I Pipes with specials for providing FHTC at Siromoni mouza within command area of Abujhati Piped W/S Scheme Jamalpur Development Block under Burdwan Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000181/2023-2024 | 1005/BSD | 06/06/2023 | 21/06/2023 | DEBASHISH ENTERPRISE | 0.94 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | Augmentation | Laying different dia UPVC Pipeline for inter connection of existing FHTC near Raypara of Abujhati Flyover i.c.w. Road widening from 4 lane to 6 lane of NH-2 at chane 601+9521+960 under ABUIHATI PWSS in jamalpur Block within Burdwan Sub Divn. under Burdwan Division, P.H.E. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001173/2023-2024 | 532/BSD | 14/03/2024 | 13/04/2024 | SOUMYAVASH DAS | 0.89 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | Augmentation | Illumination arrangement and miscelleneous works at Abujhati water supply scheme under Jamalpur Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000404/2024-2025 | 2783/CMD | 01/10/2024 | 30/11/2024 | M/S. S.R. ENTERPRISE | 19.25 | 0 | 0 | 20
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | Augmentation | Construction & Installation of Sluice valve & valve Chamber to control the flow of water with laying of u-PVC Pipe under Abujhati PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR,Junior Engineer, Burdwan Division | ORD/001293/2024-2025 | 351/AE/HQ | 10/03/2025 | 09/04/2025 | DEBASHISH ENTERPRISE | 5.47 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | Augmentation | Providing FHTC for 100% coverage at Napara, Astai, Panch Shimul, Dastanpur, Keotara, Siromani, Abujhati & Ajhapur Habitation (Village) for ABUJHATI Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000098/2023-2024 | 2236/BWD | 16/05/2023 | 03/04/2025 | PAL CONSTRUCTION | 36.63 | 0 | 0 | 50
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | Augmentation | Construction of overflow chamber with u-PVC pipe line for removal of excess water at Head work Site Under ABUJHATI PWSS Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | JE/RWS/JAMALPUR,Junior Engineer, Burdwan Division | ORD/001037/2024-2025 | 88/AE/HQ | 08/01/2025 | 07/02/2025 | SOUMYAVASH DAS | 0.97 | 0 | 0 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI | SM/15184 | Augmentation | Improvement of 300 CuM OHR (Concreting, Plastering, Primer and Painting) for Abujhati PWSS under Jamalpur Block under Burdwan Divn., PHE. Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000344/2024-2025 | 450/AE/HQ | 24/07/2024 | 07/09/2024 | DEBASHISH ENTERPRISE | 2.01 | 0 | 0 | 100
Total | [13 empty] | 104.47 | 0 | 0