## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR | SM/15185 | Augmentation | Preparation and Submission of DPR for Augmentation of Ruppur PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] |  |  | ORD/000351/2023-2024 | 1478/BSD | 12/07/2023 | 27/07/2023 | CARTO | 0.78 | 0 | 0 | 100
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR | SM/15185 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 3 at Augumentation of RUPPUR Water Supply Scheme [BLOCK- JAMALPUR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001609/2023-2024 | 1540/CMD | 05/03/2024 | 04/05/2024 | KAMAKHYA ENTERPRISE | 12.33 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR | SM/15185 | Augmentation | Providing FHTC for 100% coverage at RUPPUR & Dhuluk Habitation (Village) for RUPPUR Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000125/2023-2024 | 2315/BWD | 19/05/2023 | 18/07/2023 | MAJILA ENTERPRISE | 62.34 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR | SM/15185 | Augmentation | Relaying and replace of damaged HDPE pipeline with repairing of valve for control of water flow within command area of RUPPUR Piped W/S Scheme at Ruppur Habitation,Jamalpur Development Block under Burdwan Division PHE Dte. |  | RWS_JAMALPUR | ORD/000155/2024-2025 | 1044/BSD | 10/06/2024 | 10/07/2024 | SANDIPAN SENGUPTA | 0.65 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR | SM/15185 | Augmentation | Sinking of 300 mm X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) with construction of Pump House, Boundary wall, Land Development and Rising main connection of RUPPUR Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. [FOR 3rd. TUBE WELL SITE] | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000996/2024-2025 | 4593/BWD | 31/12/2024 | 30/04/2025 | HI-LIGHT ELECTRONICS | 26.2 | 0 | 0 | 30
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR | SM/15185 | Augmentation | Illumination arrangement and miscellaneous works at Ruppur water supply scheme under Jamalpur Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000473/2024-2025 | 2947/CMD | 20/11/2024 | 19/01/2025 | M/S. SWAPAN BANERJEE | 19.64 | 0 | 0 | 30
Total | [13 empty] | 121.94 | 0 | 0