## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR | SM/15187 | Augmentation | Construction of 3.60 mtr x 3.0 mtr size Pump House cum chlorine room with sanitary and water supply arrangement at to departmental drawing for RAMKRISHNAPUR Water Supply Scheme within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000805/2023-2024 | 4821/BWD | 08/11/2023 | 07/01/2024 | SK BADIUZZAMAL | 4.32 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR | SM/15187 | Augmentation | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of RAMKRISHNAPUR Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000015/2023-2024 | 1730/BWD | 13/04/2023 | 12/06/2023 | SUPRIYA RAY | 40.13 | 20.84 | 51.93 | 45
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR | SM/15187 | Augmentation | Designing, Making and Erection of Sign Board for SAJAL GRAM in Khemta Village, Raina - I Block within Ramkrishnapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000798/2023-2024 | 877/AE/HQ | 07/11/2023 | 07/12/2023 | PAPRI HAZRA | 0.76 | 0.72 | 95.4 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR | SM/15187 | Augmentation | Preparation and Submission of DPR for Augmentation of Ramkrishnapur PWSS under Raina-I Development Block under Burdwan Division, P.H.E Dte (2nd Call) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001224/2023-2024 | 2972/BSD | 20/12/2023 | 04/01/2024 | GEO-SOLUTION | 0.78 | 0.78 | 100 | 100
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR | SM/15187 | Augmentation | NEW SERVICE CONNECTION FOR RAMKRISHNAPUR (AUGMENTATION) PWSS TW 03 |  |  | BILL/00119/2024-2025 | BP-2024-25-57 | 26/04/2024 | 26/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.52 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR | SM/15187 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Ramkrishnapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000099/2023-2024 | 2599/CMD | 07/06/2023 | 17/04/2025 | SOUVIK HALDER | 10.42 | 9.83 | 94.35 | 90
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR | SM/15187 | Augmentation | Construction of switch rooms & Rising main at different TW site for RAMKRISHNAPUR Piped Water Supply Scheme under Raina - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000664/2023-2024 | 4163/BWD | 20/09/2023 | 01/01/2025 | LAKSHMIKANTA DAS | 8.93 | 7.79 | 87.21 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR | SM/15187 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 4TH TW site of RAMKRISHNAPUR W/S Scheme under Raina - I Block within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000205/2023-2024 | 2708/BWD | 08/06/2023 | 08/07/2023 | M/S D. PALIT & CO. | 13.25 | 10.14 | 76.59 | 100
Total | [13 empty] | 82.1 | 50.1 | 61.03