## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 |  |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR |  |  | Construction of 3.60 mtr x 3.0 mtr size Pump House cum chlorine room with sanitary and water supply arrangement at to departmental drawing for RAMKRISHNAPUR Water Supply Scheme within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000805/2023-2024 | 4821/BWD | 08/11/2023 | 07/01/2024 | SK BADIUZZAMAL | 4.32 | 0 | 0 | 0
2 |  |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR |  |  | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of RAMKRISHNAPUR Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000015/2023-2024 | 1730/BWD | 13/04/2023 | 12/06/2023 | SUPRIYA RAY | 40.13 | 20.84 | 51.93 | 45
3 |  |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR |  |  | Designing, Making and Erection of Sign Board for SAJAL GRAM in Khemta Village, Raina - I Block within Ramkrishnapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | AE(HQs) | J.E. 1 BURDWAN | ORD/000798/2023-2024 | 877/AE/HQ | 07/11/2023 | 07/12/2023 | PAPRI HAZRA | 0.76 | 0.72 | 95.4 | 100
4 |  |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR |  |  | Preparation and Submission of DPR for Augmentation of Ramkrishnapur PWSS under Raina-I Development Block under Burdwan Division, P.H.E Dte (2nd Call) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001224/2023-2024 | 2972/BSD | 20/12/2023 | 04/01/2024 | GEO-SOLUTION | 0.78 | 0.78 | 100 | 100
5 |  |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR |  |  | NEW SERVICE CONNECTION FOR RAMKRISHNAPUR (AUGMENTATION) PWSS TW 03 |  |  | BILL/00119/2024-2025 | BP-2024-25-57 | 26/04/2024 | 26/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.52 | 0 | 0 | 0
6 |  |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR |  |  | Laying Parallel Pipeline to improve drinking water supply, Construction Path Way, Drain at different TW Site and providing leftout FHTC, Road Restoration with allied work for RAMKRISHNAPUR Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000358/2024-2025 | 2913/BWD | 25/07/2024 | 01/01/2026 | T.K. BANERJEE & CO. | 26.89 | 0 | 0 | 70
Total | [13 empty] | 76.39 | 22.34 | 29.24