## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Alipur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000088/2023-2024 | 2593/CMD | 07/06/2023 | 07/07/2023 | SOUNAK ENTERPRISE | 22.73 | 10.85 | 47.72 | 50
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-II W/S Scheme at Kalsi Mouza, RASULPUR W/S Scheme at 4th TW site & ALIPUR W/S Scheme at 4th TW site under Memari-I Block under within Burdwan Sub-Division, PHE Dte. [For 3 Nos. Tube well]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000159/2023-2024 | 2455/BWD | 31/05/2023 | 30/07/2023 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 39.76 | 13.23 | 33.27 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Construction of switch rooms & Rising main at different TW site for ALIPUR Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. |  |  | ORD/000666/2023-2024 | 4162/BWD | 20/09/2023 | 19/11/2023 | M/S PALASH BISWAS | 8.12 | 7.19 | 88.52 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Preparation and Submission of DPR for Augmentation of Alipore PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000394/2023-2024 | 1582/BSD | 24/07/2023 | 08/08/2023 | MEASURE LAND | 0.78 | 0.77 | 99.01 | 100
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Quotation for new electric service connection at Alipur PH NO.-3 |  |  | BILL/01756/2023-2024 | BP-2023-24-266 | 11/12/2023 | 11/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.78 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Construction of boundary wall and Soak Well at Head Works Site, Extension of Pipe Line at Alipur Adibasipara and Installation of water level indicator of ALIPUR Water Supply Scheme under MEMARI-I Block of Burdwan Division, PHE Dte. (Length -230.00 Mtr, Col-85 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000180/2024-2025 | 2300/BWD | 20/06/2024 | 18/10/2024 | ROHAN MONDAL | 31.47 | 4.29 | 13.64 | 17
7 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 09/02/2025 | S DUTTA | 15.06 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Providing Balance Functional Household Tap Connection (800 Nos. FHTC) from existing distribution system within the command area of ALIPUR Piped Water Supply scheme at ALIPUR, AMADPUR (PART) mouza, Construction of boundary wall at 4th T/W site MEMARI-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000319/2024-2025 | 2855/BWD | 22/07/2024 | 23/03/2025 | MUKHERJEE ENTERPRISE | 84.14 | 30.02 | 35.68 | 30
9 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Illumination arrangement & different electro-mechanical works at ALIPUR water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000413/2024-2025 | 2794/CMD | 01/10/2024 | 01/01/2025 | S DUTTA | 12.53 | 12.2 | 97.37 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for ALIPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001095/2024-2025 | 430/BWD | 20/01/2025 | 01/07/2026 | DULAL MAJUMDER | 117.26 | 0 | 0 | 30
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Laying parallel 200 mm dia pipeline at Shyamnagar of Alipur pwss under Memari-I Development Block under Burdwan Division PHE Dte. |  | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000044/2025-2026 | 1026/BSD | 08/05/2025 | 07/06/2025 | ROHAN MONDAL | 4.92 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR | SM/15191 | Augmentation | Replacing damaged PVC water supply line and re installation of FHTC at Shyamnagar for Alipur and its Adjoining Mouza W/S Scheme, block -Memari-I within Burdwan Sub-Division ,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/001085/2024-2025 | 114/BSD | 16/01/2025 | 15/02/2025 | MUKHERJEE ENTERPRISE | 2.44 | 0 | 0 | 80
Total | [13 empty] | 342.99 | 78.55 | 22.9