## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 3rd Tube well site at Bagila village to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for BAGILA its Adjoining Mouza W/S scheme, block -MEMARI-I within Burdwan Sub-Division ,PHE Dte._2ND CALL |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000096/2023-2024 | 809/BSD | 03/05/2023 | 17/06/2023 | A R TRADERS | 3.6 | 0 | 0 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Laying of 150mm DI pipeline between Bagila health centre to Bagila Baroaritala for BAGILA Piped Water Supply Scheme to provide house connection under memari-I block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000336/2023-2024 | 1473/BSD | 12/07/2023 | 27/07/2023 | A R TRADERS | 0.97 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Preparation and Submission of DPR for Augmentation of Bagila PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000396/2023-2024 | 1584/BSD | 24/07/2023 | 08/08/2023 | MEASURE LAND | 0.78 | 0 | 0 | 100
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | New service connection charges for Aug. Bagila PWSS TW-3 |  |  | BILL/00769/2023-2024 | BP-2023-24-67 | 20/07/2023 | 20/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.18 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Illumination arrangement & different electro-mechanical works at BAGILA water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000414/2024-2025 | 2795/CMD | 01/10/2024 | 30/11/2024 | GOENKA ENTERPRISE | 14.16 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Bagila Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000085/2023-2024 | 2591/CMD | 07/06/2023 | 07/07/2023 | SUBRATA BHADRA | 11.09 | 0 | 0 | 50
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Interconnection between Head Work site T/W to 2nd T/W site for BAGILA Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000182/2023-2024 | 1006/BSD | 06/06/2023 | 06/07/2023 | A R TRADERS | 0.96 | 0 | 0 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Restoration Rising main line for FHTC work and Construction of boundary wall at Head work site with gate and land development, drain and internal pathway and for BAGILA PWSS under Memari-I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000904/2023-2024 | 5381/BWD | 08/12/2023 | 06/02/2024 | SK RAJU | 35.42 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Supply & delivery of standby Submersible pumping machinery & automatic Chlorinator for Bagila & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/001416/2023-2024 | 152/CMSD | 22/01/2024 | 06/02/2024 | BEHERA ENTERPRISE | 1.74 | 0 | 0 | 100
10 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Electric quotation for New Service Connection at Bagila W/S (Aug.) Scehem PH-IV. |  |  | BILL/01783/2023-2024 | BP-2023-24-291 | 26/12/2023 | 26/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Augmentation of BAGILA Piped Water Supply Scheme with sinking of Tube-well, LDS & FHTC For Songoti Pally, LDS & FHTC For Station Para & LDS & FHTC For Taktipur, Baharampur, Krishnapur, Talchina & Kiskinda Habitation under Memari-I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000172/2023-2024 | 3036/BWD | 14/07/2023 | 01/01/2025 | H SAMANTA | 149.26 | 0 | 0 | 85
12 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Providing FHTC work on distribution system for FHTC work for BAGILA Piped W/S. Scheme at berhampur, Krishnapur, Kiskinda, Taktipur mouza within Memari I Block under Burdwan Divn., PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000713/2025-2026 | 2289/BWD | 06/08/2025 | 20/09/2025 | H SAMANTA | 9.73 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Designing,making and erection of Sign Board for SWAJAL GRAM in Krishnapur village of Memari-I Block under Bagila Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos Board) |  |  | ORD/000506/2025-2026 | 2350/BSD | 21/08/2025 | 31/08/2025 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Providing balance FHTC work on distribution system for FHTC work for BAGILA Piped Water Supply Scheme at various mouza within Memari I Block under Burdwan Divn., PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000687/2025-2026 | 1407/BWD | 16/05/2025 | 30/06/2025 | H SAMANTA | 10.2 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW SITE for Aug. of BAGILA, SASINARA ZONE-I, SASINARA ZONE-II, Piped Water Supply Scheme within MEMARI-I Block under Burdwan Division, PHE. Dte. District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000974/2023-2024 | 027/BWD | 03/01/2024 | 03/03/2024 | KOUSIK MALLICK | 38.87 | 0 | 0 | 90
16 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA | SM/15192 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 4 at Augmentation of BAGILA Water Supply Scheme [ BLOCK- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001608/2023-2024 | 1537/CMD | 05/03/2024 | 31/10/2024 | SUDIKSHA CONSTRUCTION | 12.32 | 0 | 0 | 100
Total | [13 empty] | 301.42 | 0 | 0