## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Augmentation of Chhotoboinan Water Supply Scheme [ Block- Raina-II ] ( Tube Well no 4 ) under CMD, PHE Dte., Dist.- Purba-Bardhaman |  |  | ORD/000618/2022-2023 | 3142/CMD | 29/11/2022 | 29/12/2022 | CHATTERJEE ENTERPRISE | 10.99 | 10.6 | 96.53 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | Laying of Interconnection of 3rd Tube well Site of Chotobainan Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000090/2023-2024 | 737/BSD | 20/04/2023 | 05/05/2023 | BRINDABAN KONAR | 0.93 | 0.9 | 96.94 | 100
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | Providing Electrical accessories for Tube well No. 2 of Chotobainan & others Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000991/2023-2024 | 4347/CMD | 19/09/2023 | 19/10/2023 | DUTTA ENTERPRISE | 3.09 | 3.09 | 100 | 100
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Chotoboinan Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000083/2023-2024 | 2590/CMD | 07/06/2023 | 07/07/2023 | CHOUDHURY ENTERPRISE | 22.51 | 10.52 | 46.73 | 48
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of CHHOTOBAINAN (NILEDIGHIR PAR) W/S Scheme under Raina-II Block within Burdwan Sub-Division, PHE Dte. [For 01 No. Tube well]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000595/2023-2024 | 3768/BWD | 29/08/2023 | 28/09/2023 | B.S. ENTERPRISE | 13.13 | 10.52 | 80.11 | 100
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | Procurement of electro-mechanical accessories for Chotoboinan Water Supply Scheme under JJM under CMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001017/2023-2024 | 529/CMSD | 07/07/2023 | 06/08/2023 | JOYGURU ENTERPRISE | 0.84 | 0.84 | 100 | 99
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | Construction of Switch room cum chlorine room with sanitary and water supply arrangement (P.H-4) at New Tube Well Site of CHOTOBAINAN and its adjoining Mouzas Pipe Water Supply Scheme of cracky nature of soil according to departmental drawing no.-PHE/BD/P.H/DRG-01/DCE-2017, Block:- Raina-II, under Burdwan Sub-Division, P.H.E Dte. within Burdwan Division P.H.E. Dte. Dist:Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000972/2023-2024 | 001/BWD | 02/01/2024 | 02/03/2024 | CHOWDHURY CONSTRUCTION | 5.83 | 5.16 | 88.53 | 99
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | Preparation and Submission of DPR for Augmentation of Chhotobainan PWSS under Raina-II Development Block under Burdwan Division, P.H.E Dte (2nd Call) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001226/2023-2024 | 2974/BSD | 20/12/2023 | 04/01/2024 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | Improvement/ Strenthenning of RCC Elevated Reservoir (Capacity 700 Cum) & pipe line of CHOTOBAINAN PWSS for smooth running of FHTC work under RAINA-II Block, District:- Purba- Bardhaman. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000295/2024-2025 | 1277/BSD | 12/07/2024 | 10/09/2024 | ANWESHA CONSTRUCTION | 3.34 | 0 | 0 | 100
10 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | New service connection for Augmentation of Chotoboinan PWSS TW-4. |  |  | BILL/02281/2023-2024 | BP-2023-24-435 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.66 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tubwell (Replacement TW), Repairing of pump house with Boundary wall at head worksite & other related works for CHOTOBAINAN PWSS under Burdwan Sub-Div., Block -Raina-II, under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001099/2024-2025 | 435/BWD | 20/01/2025 | 20/05/2025 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 106.18 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN | SM/15194 | Augmentation | Pipeline with FHTC for CHOTOBAINAN Water Supply Scheme at Gopalpur village (400 Nos), Akhina village (250 Nos) within Raina-II Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000795/2022-2023 | 1498/BWD | 28/03/2023 | 01/12/2024 | BRINDABAN KONAR | 59.24 | 42.2 | 71.22 | 100
Total | [13 empty] | 229.51 | 84.6 | 36.86