## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DERIAPUR | SM/15195 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Astikpur, Dakhinkul & Balagar of DERIAPUR Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000762/2022-2023 | 1296/BWD | 21/03/2023 | 31/12/2024 | T.K. BANERJEE & CO. | 68.81 | 56.29 | 81.81 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DERIAPUR | SM/15195 | Retrofitting | Sinking of Tube Well, Construction of Pump House, Boundary Wall at 3rd TW Site with Extension of Pipeline & Laying Parallel line and Providing FHTC (Leftout] with allied works for DERIAPUR Piped Water Supply Scheme under Raina-I Block within Burdwan Sub Division under Burdwan Division P.H.E Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000177/2024-2025 | 2270/BWD | 18/06/2024 | 11/07/2025 | ROY CONSTRUCTION | 68.15 | 0 | 0 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DERIAPUR | SM/15195 | Retrofitting | Quotation from WBSEDCL for new service connection of Deriapur PWSS. (P.H.-3) under Burdwan Division, PHE Dte. (Application ID-5004452105, dt.-28/10/2024) |  |  | BILL/01154/2024-2025 | 1265/JJM | 31/01/2025 | 31/01/2025 | WBSEDCL | 8.35 | 0 | 0 | 0
Total | [13 empty] | 145.31 | 56.29 | 38.74