## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU | SM/15203 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of NATU W/S Scheme under Raina - I Block within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000204/2023-2024 | 2707/BWD | 08/06/2023 | 08/07/2023 | M/S D. PALIT & CO. | 13.25 | 11.23 | 84.75 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU | SM/15203 | Augmentation | Preparation and Submission of DPR for Augmentation of Natu PWSS under Raina-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000398/2023-2024 | 1586/BSD | 24/07/2023 | 08/08/2023 | GEO-SOLUTION | 0.78 | 0.77 | 99.01 | 100
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU | SM/15203 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Natu Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000097/2023-2024 | 2598/CMD | 07/06/2023 | 07/07/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 11.15 | 10.02 | 89.87 | 96
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU | SM/15203 | Augmentation | NEW SERVICE CONNECTION FOR NATU (AUGMENTATION) PWSS TW 03 |  |  | BILL/00118/2024-2025 | BP-2024-25-58 | 26/04/2024 | 26/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.49 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU | SM/15203 | Augmentation | Extension of Pipeline for providing Functional Household Tap Connection (FHTC) at Birupur & Sudarshanpur village under NATU Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001035/2023-2024 | 675/BWD | 19/02/2024 | 18/04/2025 | KALYAN CHOWDHURY | 7.49 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU | SM/15203 | Augmentation | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at Head Work Site and providing leftout FHTC, Road Restoration with allied work for NATU Piped Water Supply Scheme, Block-Raina-I within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000373/2024-2025 | 2994/BWD | 01/08/2024 | 01/12/2025 | ANWESHA CONSTRUCTION | 55.19 | 0 | 0 | 75
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU | SM/15203 | Augmentation | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Birupur & Siyali of NATU Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000813/2022-2023 | 1576/BWD | 31/03/2023 | 30/04/2025 | KALYAN CHOWDHURY | 30.88 | 22.8 | 73.85 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU | SM/15203 | Augmentation | Construction of switch rooms & Rising main at different TW site for NATU Piped Water Supply Scheme under Raina - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000667/2023-2024 | 4164/BWD | 20/09/2023 | 16/07/2024 | M/S MA TARA ENTERPRISE | 8.01 | 7.92 | 98.96 | 100
Total | [13 empty] | 137.23 | 52.74 | 38.44