## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHANDUTIA | SM/15205 | Augmentation | Preparation and Submission of DPR for Augmentation of Chandutia PWSS under Burdwan-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000348/2023-2024 | 1475/BSD | 12/07/2023 | 27/07/2023 | MEASURE LAND | 0.78 | 0.77 | 99.01 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHANDUTIA | SM/15205 | Augmentation | Providing 22 Nos.FHTC at CHANDUTIA & JAMALPUR village for declearation of SWAJALGRAM under CHANDUTIA Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000147/2024-2025 | 1033/BSD | 10/06/2024 | 26/09/2024 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.97 | 0 | 0 | 100
Total | [13 empty] | 1.74 | 0.77 | 44.11