## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina-I | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Material Requisition To Resource Division |  |  | RTOR000482/2023-2024 | 4006/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 5.14 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina-I | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 12.69 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina-I | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Material Requisition To Resource Division |  |  | RTOR000669/2023-2024 | 5083/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina-I | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | New service connection charges for Gopalpur PWSS TW-2 |  |  | BILL/01528/2023-2024 | BP-2023-24-193 | 11/10/2023 | 11/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.82 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina-I | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Restoration of hard shoulder from 0.00 km to 2.918 km of Sagrai Raina Road (MDR) for laying of water supply pipeline of Gopalpur PWSS under Burdwan Division, PHE Dte. |  |  | BILL/01127/2023-2024 | 1084/JJM | 20/12/2023 | 20/12/2023 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 4.72 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina-I | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Field level data validation of FHTC executed by Agencies on the basis of pictorial data with the objective of controlling multiple entry,improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database of GOPALPUR Pipe Water Supply Scheme in Raina-I Block within Burdwan Sub-Division under Burdwan Division,PHE Dte |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000946/2024-2025 | 2732/BSD | 10/12/2024 | 09/01/2025 | TECHVISION | 0.56 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina-I | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gopalpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000720/2023-2024 | 4031/CMD | 29/08/2023 | 28/09/2023 | M/S. SWAPAN BANERJEE | 28.98 | 23.86 | 82.33 | 100
8 | PURBA BARDHAMAN | Raina-I | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | New electric connection for Gopalpur PWSS. |  |  | BILL/01869/2023-2024 | BP-2023-24-344 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.66 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Raina-I | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
10 | PURBA BARDHAMAN | Raina-I | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 25/01/2026 | SK ALIM | 1353.91 | 0 | 0 | 25
Total | [13 empty] | 1508.51 | 23.86 | 1.58