## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME | SM/15238 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 16.04 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME | SM/15238 | New | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 10.9 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME | SM/15238 | New | Material Requisition To Resource Division |  |  | RTOR000489/2023-2024 | 4013/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 15.19 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME | SM/15238 | New | Material Requisition To Resource Division |  |  | RTOR000623/2023-2024 | 4881/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 29.6 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | RAJUR PIPED WATER SUPPLY SCHEME | SM/15238 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | RAJUR PIPED WATER SUPPLY SCHEME | SM/15238 | New | Quotation for new service connection at RAJUR W/S Scheme PH-II. |  |  | BILL/01813/2023-2024 | BP-2023-24-317 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.22 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | RAJUR PIPED WATER SUPPLY SCHEME | SM/15238 | New | New service connection charges for Rajur PWSS TW-1 |  |  | BILL/01766/2023-2024 | BP-2023-24-278 | 21/12/2023 | 21/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.15 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME | SM/15238 | New | RAJUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000007/2023-2024 | 1701/BWD | 12/04/2023 | 11/04/2024 | TEKNO ENTERPRISE | 471.14 | 430.57 | 91.39 | 77
9 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | RAJUR PIPED WATER SUPPLY SCHEME | SM/15238 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at RAJUR Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000825/2023-2024 | 4102/CMD | 29/08/2023 | 28/09/2023 | S DUTTA | 28.98 | 22.78 | 78.61 | 90
10 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME | SM/15238 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Chakta, Mahula, Rajoor and Srigram PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000284/2024-2025 | 2721/BWD | 11/07/2024 | 01/10/2025 | ESCON INDIA | 139.35 | 23.75 | 17.05 | 70
Total | [13 empty] | 799.85 | 477.11 | 59.65