## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | PURULIA PIPED WATER SUPPLY SCHEME | SM/15239 | New | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 15.02 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | PURULIA PIPED WATER SUPPLY SCHEME | SM/15239 | New | Material Requisition To Resource Division |  |  | RTOR000490/2023-2024 | 4014/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 8.73 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | PURULIA PIPED WATER SUPPLY SCHEME | SM/15239 | New | Material Requisition To Resource Division |  |  | RTOR000597/2023-2024 | 4891/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 10 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | PURULIA PIPED WATER SUPPLY SCHEME | SM/15239 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 31/10/2024 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | PURULIA PIPED WATER SUPPLY SCHEME | SM/15239 | New | New service connection at Purulia PWSS TW No.1 |  |  | BILL/02377/2023-2024 | BP-2023-24-492 | 01/02/2024 | 01/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.09 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | PURULIA PIPED WATER SUPPLY SCHEME | SM/15239 | New | NEW SERVICE CONNECTION FOR PURULIA PWSS TW 2. |  |  | BILL/03136/2023-2024 | BP-2023-24-650 | 20/03/2024 | 20/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.36 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | PURULIA PIPED WATER SUPPLY SCHEME | SM/15239 | New | Balance work of OHR, construction Concrete Road, Drum Sheet Pilling, Functional Household Tap Connection, construction of HUME Pipe culvert, land development, Road restoration etc. under Billeswar PWSS, Purulia PWSS & Gurpara PWSS under KATWA -II Block under Katwa Sub-Divn. under Burdwan Division, PHED. District:- Purba-Bardhaman | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000310/2024-2025 | 2834/BWD | 19/07/2024 | 01/11/2026 | PASCON | 190.06 | 0 | 0 | 90
8 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | PURULIA PIPED WATER SUPPLY SCHEME | SM/15239 | New | Supply and delivery of 7.5 HP pump motor set at T.W. No - 2 of PURULIA (Block- Ketugram-II) water supply scheme under CMD, PHE Dte. | Driller In-Charge | JUNIOR ENGINEER | ORD/000733/2024-2025 | 821/DIC/BMSD(D) | 05/12/2024 | 07/01/2025 | BARMAN ROY TRADERS | 0.67 | 0 | 0 | 100
9 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | PURULIA PIPED WATER SUPPLY SCHEME | SM/15239 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at PURULIA Water Supply Scheme [Block - KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Driller In-Charge | Junior Engineer | ORD/000823/2023-2024 | 4100/CMD | 29/08/2023 | 24/06/2025 | BARMAN ROY TRADERS | 21.01 | 7.97 | 37.91 | 43
Total | [13 empty] | 293.9 | 7.97 | 2.71