## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME | SM/15240 | New | Material Requisition To Resource Division |  |  | RTOR000099/2022-2023 | 1639/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 1.38 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME | SM/15240 | New | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 1245/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 9.37 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME | SM/15240 | New | Material Requisition To Resource Division |  |  | RTOR000706/2023-2024 | 5045/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KHERUA PIPED WATER SUPPLY SCHEME | SM/15240 | New | Additional quotation for New service connection charges for Kherua PWSS TW-2 |  |  | BILL/01348/2023-2024 | BP-2023-24-128 | 21/08/2023 | 21/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.03 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KHERUA PIPED WATER SUPPLY SCHEME | SM/15240 | New | New service connection charges of Kherua W/S Scheme TW-1 |  |  | BILL/00688/2023-2024 | BP-2023-24-33 | 26/06/2023 | 26/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.59 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KHERUA PIPED WATER SUPPLY SCHEME | SM/15240 | New | New service connection charges for Kherua PWSS TW-2 |  |  | BILL/01263/2023-2024 | BP-2023-24-124 | 18/08/2023 | 18/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.67 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KHERUA PIPED WATER SUPPLY SCHEME | SM/15240 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KHERUA PIPED WATER SUPPLY SCHEME | SM/15240 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHERUA Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000047/2023-2024 | 2510/CMD | 02/06/2023 | 02/07/2023 | GOENKA ENTERPRISE | 26.97 | 10.04 | 37.23 | 100
9 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME | SM/15240 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOHAGRAM, KHERUA & JABAGRAM Piped Water Supply Scheme under Mangalkote Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000697/2022-2023 | 582/BWD | 17/02/2023 | 01/01/2026 | PUSPA ENTERPRISE | 1185.88 | 239.11 | 20.16 | 75
10 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME | SM/15240 | New | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001301/2024-2025 | 936/BWD | 11/03/2025 | 07/09/2025 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0 | 0
Total | [13 empty] | 1677.09 | 249.15 | 14.86