## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | BILLESWAR PIPED WATER SUPPLY SCHEME | SM/15241 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 0.83 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | BILLESWAR PIPED WATER SUPPLY SCHEME | SM/15241 | New | Material Requisition To Resource Division |  |  | RTOR000153/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 11.05 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | BILLESWAR PIPED WATER SUPPLY SCHEME | SM/15241 | New | Material Requisition To Resource Division |  |  | RTOR000624/2023-2024 | 4870/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 29.6 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | BILLESWAR PIPED WATER SUPPLY SCHEME | SM/15241 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BILLESWAR Water Supply Scheme [ Block- KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000779/2023-2024 | 4073/CMD | 29/08/2023 | 28/09/2023 | KAMAKHYA ENTERPRISE | 26.97 | 0 | 0 | 88
5 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | BILLESWAR PIPED WATER SUPPLY SCHEME | SM/15241 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 31/10/2024 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | BILLESWAR PIPED WATER SUPPLY SCHEME | SM/15241 | New | New service connection at Billeswar PWSS TW No.1 |  |  | BILL/02374/2023-2024 | BP-2023-24-493 | 01/02/2024 | 01/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.28 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | BILLESWAR PIPED WATER SUPPLY SCHEME | SM/15241 | New | New Service connection for Billwswar PWSS TW-2 |  |  | BILL/02350/2023-2024 | BP-2023-24-466 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.04 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | BILLESWAR PIPED WATER SUPPLY SCHEME | SM/15241 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BILLESWAR, GURPARA & PURULIA Piped Water Supply Scheme under KETUGRAM-II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000038/2023-2024 | 1821/BWD | 18/04/2023 | 01/10/2025 | PASCON | 1118.33 | 0 | 0 | 46
9 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | BILLESWAR PIPED WATER SUPPLY SCHEME | SM/15241 | New | Balance work of OHR, construction Concrete Road, Drum Sheet Pilling, Functional Household Tap Connection, construction of HUME Pipe culvert, land development, Road restoration etc. under Billeswar PWSS, Purulia PWSS & Gurpara PWSS under KATWA -II Block under Katwa Sub-Divn. under Burdwan Division, PHED. District:- Purba-Bardhaman | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000310/2024-2025 | 2834/BWD | 19/07/2024 | 01/11/2026 | PASCON | 190.06 | 0 | 0 | 90
Total | [13 empty] | 1425.1 | 0 | 0