## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MAHATA Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000822/2023-2024 | 4099/CMD | 29/08/2023 | 28/09/2023 | BENGAL CONSTRUCTION. | 27.79 | 21.39 | 76.98 | 90
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENRIA, MAHATA, DEBPUR Piped Water Supply Scheme under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000019/2023-2024 | 1737/BWD | 13/04/2023 | 31/12/2025 | M/S B. RAI CONSTRUCTION COMPANY | 1643.39 | 200.99 | 12.23 | 81
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 45.74 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | Material Requisition To Resource Division |  |  | RTOR000169/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 5.19 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | Material Requisition To Resource Division |  |  | RTOR000578/2023-2024 | 4926/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 37.58 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period AUG.'2024 to OCT.'2024] |  |  | ORD/000845/2024-2025 | 575/DSD | 19/07/2024 | 05/10/2024 | MD HASIN | 1 | 0.33 | 33.33 | 0
8 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | ADDITIONAL CONNECTION FOR MAHATA PWSS PH-1. |  |  | BILL/02875/2023-2024 | BP-2023-24-599 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.1 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | New service connection charges for Mahata PWSS TW-1 |  |  | BILL/01830/2023-2024 | BP-2023-24-338 | 06/01/2024 | 06/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.54 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | New Service connection at Mahata PWSS PH-1 |  |  | BILL/02318/2023-2024 | BP-2023-24-538 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.24 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Bhatar | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | FOR FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING SCHEME DESCRIPTION AT KHEJURHATI PWSS AND OTHER SCHEMES ( 16 Nos) WITHIN BHATAR BLOCK UNDER BURDWAN DIVISION , PHE Dte. |  |  | ORD/001422/2024-2025 | 298/DSD | 20/02/2025 | 13/03/2025 | SHUBHRA KANTI GHOSH | 1.39 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Bhatar | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME | SM/15242 | New | Material Requisition To Resource Division |  |  | RTOR000073/2024-2025 | 399/BWD | 17/01/2025 | 17/01/2025 | Resource Division | 5.59 | 0 | 0 | 0
Total | [13 empty] | 1875.54 | 222.72 | 11.87