## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME | SM/15244 | New | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 1248/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 1.91 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME | SM/15244 | New | Material Requisition To Resource Division |  |  | RTOR000751/2023-2024 | 5248/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 18.5 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Central Mechanical | KARJJANA PIPED WATER SUPPLY SCHEME | SM/15244 | New | New service connection charges for Karjjana PWSS TW-1 |  |  | BILL/00753/2023-2024 | BP-2023-24-53 | 18/07/2023 | 18/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.66 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Central Mechanical | KARJJANA PIPED WATER SUPPLY SCHEME | SM/15244 | New | New service connection charges for Karjjana PWSS TW-2 |  |  | BILL/00754/2023-2024 | BP-2023-24-54 | 14/07/2023 | 14/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.43 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | KARJJANA PIPED WATER SUPPLY SCHEME | SM/15244 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME | SM/15244 | New | KARJJANA [PART :-A] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000721/2022-2023 | 955/BWD | 03/03/2023 | 02/05/2023 | DHIRENDRANATH SOM | 44.51 | 35.31 | 79.33 | 100
7 | PURBA BARDHAMAN | Bhatar | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME | SM/15244 | New | KARJJANA [PART :-B] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000722/2022-2023 | 956/BWD | 03/03/2023 | 02/05/2023 | DHIRENDRANATH SOM | 45.79 | 30.55 | 66.71 | 95
8 | PURBA BARDHAMAN | Bhatar | Central Mechanical | KARJJANA PIPED WATER SUPPLY SCHEME | SM/15244 | New | New service connection for KARJANA PWSS, PH-2. |  |  | BILL/02486/2023-2024 | BP-2023-24-535 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.06 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Bhatar | Central Mechanical | KARJJANA PIPED WATER SUPPLY SCHEME | SM/15244 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KARJJANA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000061/2023-2024 | 2521/CMD | 02/06/2023 | 29/03/2026 | MITRA ASSOCIATES | 27.66 | 21.37 | 77.28 | 95
10 | PURBA BARDHAMAN | Bhatar | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME | SM/15244 | New | Additional Distribution Pipeline work at KARJJANA Piped Water Supply Scheme with Rising Main, LDS & FHTC work under Bhatar Block, District:- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/001045/2023-2024 | 789/BWD | 27/02/2024 | 28/03/2024 | DHIRENDRANATH SOM | 6.2 | 6.2 | 99.99 | 100
11 | PURBA BARDHAMAN | Bhatar | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME | SM/15244 | New | FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING LAND DESCRIPTION AT KARJJANA PWSS AND OTHER SCHEMES (30 Nos.) WITHIN BHATAR BLOCK UNDER BURDWAN DIVISION , PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000945/2024-2025 | 1085/DSD | 11/12/2024 | 26/12/2024 | SHUBHRA KANTI GHOSH | 1.95 | 0.45 | 23.26 | 100
Total | [13 empty] | 237.67 | 93.89 | 39.5