## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME | SM/15246 | New | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 8.61 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME | SM/15246 | New | Material Requisition To Resource Division |  |  | RTOR000586/2023-2024 | 4930/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 34.57 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME | SM/15246 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 31.52 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Central Mechanical | DHENRIA PIPED WATER SUPPLY SCHEME | SM/15246 | New | New service connection charges for Dhenria PWSS TW-1 |  |  | BILL/01418/2023-2024 | BP-2023-24-147 | 31/08/2023 | 31/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | DHENRIA PIPED WATER SUPPLY SCHEME | SM/15246 | New | New service connection charges for Dhenria PWSS TW-2 |  |  | BILL/01473/2023-2024 | BP-2023-24-167 | 27/09/2023 | 27/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.71 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | DHENRIA PIPED WATER SUPPLY SCHEME | SM/15246 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DHENRIA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000559/2023-2024 | 3872/CMD | 17/08/2023 | 16/09/2023 | M/S, S.S. ENTERPRISE. | 27.79 | 21.41 | 77.06 | 90
7 | PURBA BARDHAMAN | Bhatar | Central Mechanical | DHENRIA PIPED WATER SUPPLY SCHEME | SM/15246 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Bhatar | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME | SM/15246 | New | Material Requisition To Resource Division |  |  | RTOR000782/2023-2024 | 325/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 6.44 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Bhatar | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME | SM/15246 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENRIA, MAHATA, DEBPUR Piped Water Supply Scheme under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000019/2023-2024 | 1737/BWD | 13/04/2023 | 31/12/2025 | M/S B. RAI CONSTRUCTION COMPANY | 1643.39 | 251.96 | 15.33 | 81
10 | PURBA BARDHAMAN | Bhatar | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME | SM/15246 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day. [PeriodFebruary.'2025 to April'2025] |  |  | ORD/001180/2024-2025 | 129/DSD | 29/01/2025 | 17/04/2025 | MD HASIN | 1 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Bhatar | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME | SM/15246 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period NOV.'2024 to JAN.'2025] |  |  | ORD/000847/2024-2025 | 886/DSD | 21/10/2024 | 07/01/2025 | MD HASIN | 1 | 0.33 | 33.33 | 0
Total | [13 empty] | 1845.3 | 273.7 | 14.83