## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Head Works & 2nd Tube well Site for BORSHUL (Zone-I) Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000193/2023-2024 | 2691/BWD | 08/06/2023 | 23/07/2023 | J K CORPORATION | 19.84 | 18.99 | 95.7 | 100
2 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | New service connection charges for Borshul PWSS Z-I TW-2 |  |  | BILL/01413/2023-2024 | BP-2023-24-142 | 28/08/2023 | 28/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.63 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | New service connection charges for Borshul PWSS Z-I TW-1 |  |  | BILL/01412/2023-2024 | BP-2023-24-141 | 28/08/2023 | 28/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 2nd Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17 (Size3.60mtrx3.00mtr room) for Barsul Zone-1 its Adjoining Mouza W/S Scheme, Block -Burdwan-II within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000575/2023-2024 | 2040/BSD | 24/08/2023 | 08/10/2023 | DEBJYOTI GOSWAMI | 3.19 | 2.61 | 81.68 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/07/2025 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
6 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Construction of internal pathway , approch road and Ohr Plinth protection at head work site for Borshul Z-I PWSS under Bardhaman-II block within Burdwan Div.PHE Dte. |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000655/2025-2026 | 1412/BSD | 17/06/2025 | 17/07/2025 | RADHAKRISHNA ENTERPRISE | 2.62 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Allied work for construction of pump house including plinth protection with surface drain at head work TW site for Borshul Z-I PWSS under Bardhaman-II block within Burdwan Div.PHE Dte. |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000779/2025-2026 | 1470/BSD | 23/06/2025 | 22/08/2025 | DAWN ASSOCIATES | 2.57 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Augmentation of Borshul (Zone-I) Piped Water Supply Scheme (Mouzas:- Barshul, Tatkhanda & Dakshin Goplapur) with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under BARDHAMAN- II Block, District:- Purba-Burdwan. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000700/2022-2023 | 616/BWD | 17/02/2023 | 31/12/2024 | ASHOK KUMAR GHOSH | 331.77 | 251.14 | 75.7 | 51
Total | [13 empty] | 678.22 | 272.73 | 40.21