## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Head Works & 2nd Tube well Site for BORSHUL (Zone-I) Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000193/2023-2024 | 2691/BWD | 08/06/2023 | 23/07/2023 | J K CORPORATION | 19.84 | 18.99 | 95.7 | 100
2 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | New service connection charges for Borshul PWSS Z-I TW-2 |  |  | BILL/01413/2023-2024 | BP-2023-24-142 | 28/08/2023 | 28/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.63 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | New service connection charges for Borshul PWSS Z-I TW-1 |  |  | BILL/01412/2023-2024 | BP-2023-24-141 | 28/08/2023 | 28/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 2nd Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17 (Size3.60mtrx3.00mtr room) for Barsul Zone-1 its Adjoining Mouza W/S Scheme, Block -Burdwan-II within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000575/2023-2024 | 2040/BSD | 24/08/2023 | 08/10/2023 | DEBJYOTI GOSWAMI | 3.19 | 2.61 | 81.68 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Allied work for construction of pump house including plinth protection with surface drain at head work TW site for Borshul Z-I PWSS under Bardhaman-II block within Burdwan Div.PHE Dte. |  | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000779/2025-2026 | 1470/BSD | 23/06/2025 | 22/08/2025 | DAWN ASSOCIATES | 2.57 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Augmentation of Borshul (Zone-I) Piped Water Supply Scheme (Mouzas:- Barshul, Tatkhanda & Dakshin Goplapur) with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under BARDHAMAN- II Block, District:- Purba-Burdwan. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000700/2022-2023 | 616/BWD | 17/02/2023 | 31/12/2024 | ASHOK KUMAR GHOSH | 331.77 | 251.14 | 75.7 | 51
7 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Construction of pump house including plinth protection with surface drain at Head Work TW site for (3.6 mtr. x 3.0 mtr. Size) Borshul Zone-I water supply schemes, Block-Burdwan-II within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000970/2023-2024 | 006/BWD | 02/01/2024 | 31/12/2024 | DAWN ASSOCIATES | 4.53 | 0 | 0 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Construction of boundary wall at 1ST TUBE WALL (HEAD WORK) Site of BARSUL Zone-I Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. Length =100.00 Mtr, Col-35 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000277/2024-2025 | 2692/BWD | 10/07/2024 | 29/12/2024 | RAHAMAN ENTERPRISE | 6.8 | 0 | 0 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN | SM/15309 | Augmentation | Construction of boundary wall at 2ND TUBE WELL Site & Sanitary of BARSUL Zone-I Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. (Length =80.00 Mtr, Col-27 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000473/2024-2025 | 3133/BWD | 16/08/2024 | 16/03/2025 | SK BADIUZZAMAL | 5.77 | 0 | 0 | 100
Total | [13 empty] | 383.1 | 272.73 | 71.19